## Document Guide
UNDERSTANDING THIS DOCUMENT
PURPOSE: | This document lists all upcoming Track Possessions for the ARTC Interstate Network. The document contains multiple worksheets that break down the full listing into their respective states for ease of reading. If there are any information conflicts, refer to the 'All Possessions' sheet
PUBLISHER: | The Interstate Possesisons Team maintain the Interstate Possessions Calendar (this document) and are the contatc point for any questions or enquiries relating to the document. Email: interstatepossessions@artc.com.au
REQUEST STATUS | Each Request listed is assigned a status depending on its progression through the approval process. Approved: The track possession will proceed as planned. Supported: The possession request has been endorsed for approval by the ARTC business unit, subject to ongoing stakeholder feedback. Pending: The possession request is still subject to ongoing review and has not yet been endorsed by the ARTC business unit Cancelled: A previously listed possession that will not proceed
IMPACT RATINGS | 1 | A track possession where both passenger and freight services are impacted by a possession that: • Impacts services scheduled to operate through the network where there are service cancellations, or • is a track possession that exceeds a duration of 10 continuous hours in length. Adhoc trains are not able to operate through the affected area.
| 2 | A track possession where mandatory freight & passenger services are impacted in a way that they require a temporary path variation: • to alter the route of a planned service, or • the timings of the planned service. A track possession that requires the implementation of a method of special working (e.g. Pilot Staff Working), or, bidirectional working, to continue to operate services – limiting available network capacity. Adhoc trains are generally not able to operate through the affected area, unless allowed by exception
| 3 | A track possession where mandatory freight services are not impacted, and the possession window is approved “Clear of mandatory services” only. Passenger services are not impacted. Adhoc trains are not able to operate through the affected area. A track possession taken on a Crossing Loop or Siding, that may affect overall network capacity or provide a service to a load point.
| 4 | A track possession where the timings of passenger and mandatory freight services are not impacted. Adhoc trains may not be able to operate through the affected area, subject to path availability.
| 5 | A track possession that is approved to operate As Traffic Permits, that does not restrict the operation of the network.
| 6 | Reserved for the use for scheduling Special Events, Additional trains, Ultrasonic Testing & other information relevant to the Annual Possession Plan
| 1P | A track possession where passenger services are impacted in a way that they require either: • major path variation, • commence/terminate short at stations, or • cancellation. Where mandatory freight services can run with a temporary variation to the MTP, and/or diverted to another route. Adhoc trains are not able to operate through the affected area.
| 1F | A Special Event occurring where freight services are impacted in a way that may require either: • temporary path variation, or • cancellation. And, where additional passenger services are provided to service the event. These are included in the annual possession plan to avoid the scheduling of a track possession during a major event, and, to prevent cumulative impacts along the path of a planned service. Adhoc trains may not be able to operate through the affected area, subject to path availability.

## ARTC IS - All Possessions
Request_ID | Customer Advised | Possessions Status | TAA # | Date Published | Operator Impact | Possession Type | Location From | Location To | Track | Start Time | Finish Time | Total Duration(hr) | Scope of Work | Corridor | Line Segments Affected | Comments for Customers | Assigned | Contact Person for the Request | Safe Working Limits (From) | Safeworking Requirements | Date Submitted
IPR-2669 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-06-24 09:00 | 2024-06-24 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2960 | 2024-06-19 | Approved | 0927-2024 | 2024-06-20 | 3 | Urgent Possession | Enfield West | Leightonfield | SSFL | 2024-06-24 12:30 | 2024-06-24 23:00 | 10:30 | Sefton Dive Pump | North - South | Southern Sydney Freight Line | Windows for ad hocs will be 1630-1800hrs and 1900-2030hrs. Mandatories as planned. | Andrew Duncan | Jensen Kelly | EW418 Signal to LF4 and LF6 Signals |  | 2024-06-18
IPR-2723 | 2024-05-16 | Approved | 0731-2024 | 2024-05-17 | 3 | Total Possession | Harden | Yass Jct | Up and Down Main | 2024-06-24 13:00 | 2024-06-24 16:30 | 3:30 | Resurfacing | North - South | Goulburn to Junee | 0700-0800, Up Main, Harden to Galong. 0800-1000, Up Main, Galong to Yass Junction. 1200-1500, Down Main, Yass Junction to Harden | Andrew Duncan | Curtis McClelland |  |  | 2024-04-23
IPR-2898 | 2024-04-30 | Approved | 0001-2024 | 2024-04-30 | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-06-24 13:00 | 2024-06-24 17:00 | 4:00 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. Train Alterations will be on TAA 0531-2024 | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2024-04-24
IPR-2324-1786 | 2023-08-24 | Approved | 0019-2024 | 2023-12-08 | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-24 16:00 | 2024-06-24 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2066 | 2023-12-22 | Approved | 0774-2024 | 2024-05-24 | 2 | Total Possession | Crystal Brook | Coonamia | East Bound Mainline | 2024-06-24 20:30 | 2024-06-25 10:30 | 14:00 | Level crossing upgrade Milcowie Rd 13.714km | East - West | Crystal Brook to Spencer Junction | No Train Period on the Eastbound Mainline Only | Neil Doust | Jessica Tai |  |  | 2023-12-18
IPR-2328 | 2024-02-26 | Approved | 0880-2024 | 2024-06-07 | 2 | Total Possession | Murtoa Loop | Marmalake | Main Line | 2024-06-25 06:00 | 2024-06-25 18:00 | 12:00 | 27D Pts VX Upgrade 298.365km | East - West | Tottenham to Serviceton | ​​No Train Period | Bryce Gore | Omid Hosseini |  |  | 2024-02-20
IPR-2407 | 2024-03-25 | Approved | 0735-2024 | 2024-05-24 | 3 | Window Possession | Seymour | Benalla | East / West Track | 2024-06-25 06:00 | 2024-06-25 18:00 | 12:00 | Ultrasonic Testing | North - South | Albury to Somerton | Critical compliance testing. No ad hoc services. Specific Locations/times TBC. | Neil Doust | David Knee
IPR-2603 | 2024-04-23 | Approved | 0749-2024 | 2024-05-10 | 2 | Total Possession | Benalla | Oaklands | Branch Line | 2024-06-25 06:00 | 2024-06-25 18:00 | 12:00 | Level Crossing Upgrades | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2024-04-08
IPR-2797 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-25 08:00 | 2024-06-25 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2724 | 2024-05-16 | Approved | 0731-2024 | 2024-05-17 | 3 | Total Possession | Yass Jct | Harden | Up and Down Main | 2024-06-25 08:30 | 2024-06-25 15:30 | 7:00 | Resurfacing | North - South | Goulburn to Junee | 0830-1100, Down Main, Yass Junction to Harden. 1300-1530, Yass Junction, Up Main within Yard Limits. | Andrew Duncan | Curtis McClelland |  |  | 2024-04-23
IPR-2670 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-06-25 09:00 | 2024-06-25 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1974 | 2023-11-24 | Cancelled |  |  | 2 | Total Possession | Coondambo | Kultanaby | Mainline | 2024-06-25 13:00 | 2024-06-26 01:00 | 12:00 | Culvert replacement 379.131km | East - West | Spencer Junction to Tarcoola | No Train Period - Was 30 April | Bryce Gore | Bonnar Mahains |  |  | 2023-11-23
IPR-2067 | 2023-12-22 | Approved | 0774-2024 | 2024-05-24 | 2 | Total Possession | Crystal Brook | Coonamia | East Bound Mainline | 2024-06-25 22:20 | 2024-06-26 10:00 | 11:40 | Level crossing upgrade Milcowie Rd 13.714km | East - West | Crystal Brook to Spencer Junction | No Train Period on the Eastbound Mainline Only | Neil Doust | Jessica Tai |  |  | 2023-12-18
IPR-1978 | 2023-11-24 | Approved | 0648-2024 | 2024-05-06 | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-06-25 22:30 | 2024-06-26 10:30 | 12:00 | Culvert Replacement: 28.272km & 37.871km | East - West | Broken Hill to Crystal Brook | Was 04-09 June 2024Amendment published 16/05/2024 | Neil Doust | Bonnar Mahains |  |  | 2023-11-23
IPR-2408 | 2024-03-25 | Approved | 0735-2024 | 2024-05-24 | 3 | Window Possession | Benalla | Wodonga | East / West Track | 2024-06-26 06:00 | 2024-06-26 18:00 | 12:00 | Ultrasonic Testing | North - South | Albury to Somerton | Critical compliance testing. No ad hoc services. Specific Locations/times TBC. | Neil Doust | David Knee
IPR-2975 | 2024-04-23 | Approved | 0749-2024 | 2024-05-10 | 2 | Total Possession | Benalla | Oaklands | Branch Line | 2024-06-26 06:00 | 2024-06-26 18:00 | 12:00 | Level Crossing Upgrades | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2024-04-08
IPR-2798 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-26 08:00 | 2024-06-26 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2671 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-06-26 09:00 | 2024-06-26 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1975 | 2023-11-24 | Cancelled |  |  | 2 | Total Possession | Coondambo | Kultanaby | Mainline | 2024-06-26 11:00 | 2024-06-26 15:30 | 4:30 | Culvert replacement 379.131km | East - West | Spencer Junction to Tarcoola | No Train Period - was 1st May | Bryce Gore | Bonnar Mahains |  |  | 2023-11-23
IPR-1979 | 2023-11-24 | Approved | 0648-2024 | 2024-05-06 | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-06-26 20:15 | 2024-06-27 02:00 | 5:45 | Culvert Replacement: 28.272km & 37.871km | East - West | Broken Hill to Crystal Brook | Was 04-09 June 2024Amendment published 16/05/2024 | Neil Doust | Bonnar Mahains |  |  | 2023-11-23
IPR-2409 | 2024-03-25 | Approved | 0735-2024 | 2024-05-24 | 3 | Window Possession | Benalla | Wodonga | East / West Track | 2024-06-27 06:00 | 2024-06-27 18:00 | 12:00 | Ultrasonic Testing | North - South | Albury to Somerton | Critical compliance testing. No ad hoc services. Specific Locations/times TBC. | Neil Doust | David Knee
IPR-2976 | 2024-04-23 | Approved | 0749-2024 | 2024-05-10 | 2 | Total Possession | Benalla | Oaklands | Branch Line | 2024-06-27 06:00 | 2024-06-27 18:00 | 12:00 | Level Crossing Upgrades | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2024-04-08
IPR-2725 | 2024-05-16 | Approved | 0732-2024 | 2024-05-17 | 3 | Total Possession | Moss Vale | Dombarton | Single Main | 2024-06-27 07:00 | 2024-06-27 12:00 | 5:00 | Resurfacing | North - South | Macarthur to Moss Vale | Resurfacing on Single Main. No trains through window. | Andrew Duncan | Curtis McClelland |  |  | 2024-04-23
IPR-2799 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-27 08:00 | 2024-06-27 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2672 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-06-27 09:00 | 2024-06-27 17:00 | 8:00 | Inland Rail - Seymour Avenal | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2410 | 2024-03-25 | Approved | 0735-2024 | 2024-05-24 | 3 | Window Possession | Benalla | Oaklands | Single Main | 2024-06-28 06:00 | 2024-06-28 12:00 | 6:00 | Ultrasonic Testing | North - South | Benalla to Oakland Line | Critical compliance testing. No ad hoc services. Specific Locations/times TBC. | Neil Doust | David Knee
IPR-2726 | 2024-05-16 | Approved | 0732-2024 | 2024-05-17 | 3 | Total Possession | Moss Vale | Dombarton | Single Main | 2024-06-28 08:00 | 2024-06-28 18:30 | 10:30 | Resurfacing | North - South | Macarthur to Moss Vale | Resurfacing between Mandatory trains. 0800-1130 then 1530-1830. | Andrew Duncan | Curtis McClelland |  |  | 2024-04-23
IPR-2800 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-28 08:00 | 2024-06-28 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2673 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-06-28 09:00 | 2024-06-28 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2901 | 2024-05-23 | Approved | 0816-2024 | 2024-05-27 | 3 | Window Possession | Goulburn | Lynwood | Up Main | 2024-06-28 10:00 | 2024-06-28 17:00 | 7:00 | Ultrasonic Testing | North - South | Moss Vale to Goulburn | Critical compliance testing, Adhos with approval,MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-1980 | 2023-11-24 | Approved | 0648-2024 | 2024-05-06 | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-06-29 03:00 | 2024-06-29 15:00 | 12:00 | Culvert Replacement: 28.272km & 37.871km | East - West | Broken Hill to Crystal Brook | Was 04-09 June 2024Amendment published 16/05/2024 | Neil Doust | Bonnar Mahains |  |  | 2023-11-23
IPR-2079 | 2023-11-30 | Approved | 0689-2024 | 2024-06-14 | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-06-29 06:00 | 2024-06-29 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 53 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2411 | 2024-03-25 | Approved | 0735-2024 | 2024-05-24 | 3 | Window Possession | Benalla | Oaklands | Single Main | 2024-06-29 06:00 | 2024-06-29 18:00 | 12:00 | Ultrasonic Testing | North - South | Benalla to Oakland Line | Critical compliance testing. No ad hoc services. Specific Locations/times TBC. | Neil Doust | David Knee
IPR-2922 | 2024-06-14 | Approved | 0898-2024 | 2024-06-14 | 1 | Total Possession | Cootamundra | Cootamundra | All | 2024-06-29 06:00 | 2024-06-29 12:30 | 6:30 | URGENT Gundagai Rd L/Xing software upgrades | North - South | Goulburn to Junee | NO AD HOCS | Neil Doust | Akhil Chopra |  |  | 2024-06-14
IPR-2089 | 2023-11-30 | Approved | 0689-2024 | 2024-06-14 | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-06-29 06:30 | 2024-06-29 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-2801 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-29 08:00 | 2024-06-29 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2825 | 2024-05-17 | Approved | 0786-2024 | 2024-06-04 | 2 | Total Possession | Tottenham | Tottenham | Brooklyn Leg of Tottenham Triangle | 2024-06-29 21:00 | 2024-06-30 16:00 | 19:00 | Tottenham Triangle Mixed Gauge Diamong Upgrade | East - West | Melbourne Metro | No Main or Broad Gauge services on Brooklyn Leg of Triangle | Bryce Gore | Ryan Sliwinski |  |  | 2024-05-01
IPR-2918 | 2024-02-26 | Approved | 0837-2024 | 2024-06-07 | 2 | Total Possession | Newport | Tottenham | All Lines | 2024-06-29 21:00 | 2024-06-30 09:00 | 12:00 | Sommerville Rd Brooklyn Boom | East - West | Tottenham to Serviceton | ​​No Train Period | Bryce Gore | Omid Hosseini |  |  | 2024-02-20
IPR-2324-80 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2024-06-29 22:00 | 2024-06-30 06:00 | 8:00 | RCP Under track Crossing | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km-20.75 km |  | 2022-09-07
IPR-2920 | 2024-06-08 | Approved | 0878-2024 | 2024-06-07 | 2 | Total Possession | Sims St Jct | West Footscray | All Lines | 2024-06-29 22:30 | 2024-06-30 07:00 | 8:30 | Tamping & rail Scrubbing | East - West | Melbourne Metro | ​​No Train Period - No Access to Tottenham Yard | Bryce Gore | Stephen Maguire |  |  | 2024-02-20
IPR-2324-441 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-06-30 00:05 | 2024-06-30 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1981 | 2023-11-24 | Approved | 0648-2024 | 2024-05-06 | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-06-30 03:30 | 2024-06-30 09:30 | 6:00 | Culvert Replacement: 28.272km & 37.871km | East - West | Broken Hill to Crystal Brook | Was 04-09 June 2024Amendment published 16/05/2024 | Neil Doust | Bonnar Mahains |  |  | 2023-11-23
IPR-2412 | 2024-03-25 | Approved | 0735-2024 | 2024-05-24 | 3 | Window Possession | Wodonga | Benalla | East / West Track | 2024-06-30 06:00 | 2024-06-30 18:00 | 12:00 | Ultrasonic Testing | North - South | Albury to Somerton | Critical compliance testing. No ad hoc services. Specific Locations/times TBC. | Neil Doust | David Knee
IPR-2802 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-30 08:00 | 2024-06-30 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2902 | 2024-05-23 | Approved | 0816-2024 | 2024-05-27 | 3 | Window Possession | Goulburn | Lynwood | Up Main | 2024-06-30 10:00 | 2024-06-30 17:00 | 7:00 | Ultrasonic Testing | North - South | Moss Vale to Goulburn | Critical compliance testing, Adhos with approval,MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2843 | 2024-05-23 | Approved | 0909-2024 | 2024-06-20 | 3 | Window Possession | Yass Jct | Joppa Jct | Up and Down Main | 2024-07-01 04:30 | 2024-07-01 14:00 | 9:30 | Resurfacing | North - South | Goulburn to Junee | 0430-0730, 0930-1100 Up Main. Then 1100-1400 Down Main | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2961 | 2024-06-19 | Approved | 0927-2024 | 2024-06-20 | 3 | Window Possession | Enfield West | Leightonfield | SSFL | 2024-07-01 07:00 | 2024-07-01 09:00 | 2:00 | Sefton Dive Pump | North - South | Southern Sydney Freight Line | No ad hocs. Mandatories as planned. | Andrew Duncan | Jensen Kelly | EW418 Signal to LF4 and LF6 Signals |  | 2024-06-18
IPR-2803 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-01 08:00 | 2024-07-01 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2674 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-01 09:00 | 2024-07-01 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2962 | 2024-06-19 | Approved | 0927-2024 | 2024-06-20 | 3 | Window Possession | Enfield West | Leightonfield | SSFL | 2024-07-01 13:00 | 2024-07-01 16:30 | 3:30 | Sefton Dive Pump | North - South | Southern Sydney Freight Line | No ad hocs. Mandatories as planned. | Andrew Duncan | Jensen Kelly | EW418 Signal to LF4 and LF6 Signals |  | 2024-06-18
IPR-2015 | 2023-08-24 | Approved | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-07-01 16:00 | 2024-07-01 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2844 | 2024-05-23 | Approved | 0909-2024 | 2024-06-20 | 3 | Window Possession | Yass Jct | Goulburn | Up and Down Main | 2024-07-02 07:30 | 2024-07-02 14:00 | 6:30 | Resurfacing | North - South | Goulburn to Junee | 0730-1000 + 1130-1400 Down Main. | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2804 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-02 08:00 | 2024-07-02 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2675 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-02 09:00 | 2024-07-02 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2805 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-03 08:00 | 2024-07-03 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2845 | 2024-05-23 | Approved | 0909-2024 | 2024-06-20 | 3 | Window Possession | Goulburn | Lynwood | Up and Down Main | 2024-07-03 08:30 | 2024-07-03 17:00 | 8:30 | Resurfacing | North - South | Moss Vale to Goulburn | 0830-1000 + 1500-1700 Up Main. Then 1030-1230 + 1315-1415 Down Main. | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2676 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-03 09:00 | 2024-07-03 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2806 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-04 08:00 | 2024-07-04 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2677 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-04 09:00 | 2024-07-04 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2678 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-05 09:00 | 2024-07-05 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2826 | 2024-05-17 | Approved | 0786-2024 | 2024-06-04 | 2 | Total Possession | Tottenham | Tottenham | Brooklyn Leg of Tottenham Triangle | 2024-07-06 21:00 | 2024-07-07 08:00 | 11:00 | Tottenham Triangle Mixed Gauge Diamong Upgrade | East - West | Melbourne Metro | No Main or Broad Gauge services on Brooklyn Leg of Triangle | Bryce Gore | Ryan Sliwinski |  |  | 2024-05-01
IPR-2827 | 2024-05-17 | Approved | 0786-2024 | 2024-06-04 | 2 | Total Possession | Tottenham | Tottenham | Up & Down Broad Gauge Indepenant Goods Lines | 2024-07-06 21:00 | 2024-07-07 10:00 | 13:00 | Tottenham Triangle Mixed Gauge Diamong Upgrade | East - West | Melbourne Metro | No Broad Gauge services through to Sunshine/Albion-Jacana | Bryce Gore | Ryan Sliwinski |  |  | 2024-05-01
IPR-1985 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-07-07 00:05 | 2024-07-07 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2828 | 2024-05-17 | Approved | 0786-2024 | 2024-06-04 | 2 | Total Possession | Tottenham | Tottenham | Brooklyn Leg and Up & Down Independant Goods Legs of Tottenham Triangle | 2024-07-07 12:00 | 2024-07-07 16:00 | 4:00 | Tottenham Triangle Mixed Gauge Diamong Upgrade | East - West | Melbourne Metro | No Main or Broad Gauge services | Bryce Gore | Ryan Sliwinski |  |  | 2024-05-01
IPR-2737 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-08 09:00 | 2024-07-08 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2903 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 3 | Total Possession | Mile End | Islington | Main Line | 2024-07-08 11:30 | 2024-07-08 17:30 | 6:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | Michael Iannella | Signal 1 Mile End to Signal 30 Islington |  | 2024-05-27
IPR-2925 | 2023-08-24 | Approved | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-07-08 16:00 | 2024-07-08 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2807 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-09 08:00 | 2024-07-09 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2741 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-09 09:00 | 2024-07-09 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2808 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-10 08:00 | 2024-07-10 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2742 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-10 09:00 | 2024-07-10 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2100 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Acacia Ridge | Tamrookum | Main Line, Loop Line | 2024-07-10 09:30 | 2024-07-10 17:00 | 7:30 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | AR1 to TM8 | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-1859 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 2 | Total Possession | Mile End | Islington | Main Line | 2024-07-10 20:30 | 2024-07-11 05:30 | 9:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period - Was June | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-2846 | 2024-05-23 | Approved | 0910-2024 | 2024-06-20 | 3 | Window Possession | Narwonah AWB | Goobang Jct | Single Main | 2024-07-11 07:00 | 2024-07-11 19:00 | 12:00 | Resurfacing | North - South | Parkes to Narromine Line | Timjelly - Peak Hill | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2809 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-11 08:00 | 2024-07-11 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2101 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Greenbank | Loadstone | Main Line, Loop Line | 2024-07-11 08:30 | 2024-07-11 16:00 | 7:30 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | GK1 to LE5 and LE7 | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2743 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-11 09:00 | 2024-07-11 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2909 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 3 | Total Possession | Mile End | Islington | Main Line | 2024-07-11 22:00 | 2024-07-12 03:30 | 5:30 | TRJ Project | East - West | Serviceton to Islington (SA) | No Adhoc Traffic - Moved from 1st July | Bryce Gore | Michael Iannella | Signal 1 Mile End to Signal 30 Islington |  | 2024-05-27
IPR-2847 | 2024-05-23 | Approved | 0910-2024 | 2024-06-20 | 3 | Window Possession | Narwonah AWB | Goobang Jct | Single Main | 2024-07-12 07:00 | 2024-07-12 19:00 | 12:00 | Resurfacing | North - South | Parkes to Narromine Line | Peak Hill - Goobang Junction | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2810 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-12 08:00 | 2024-07-12 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2744 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-12 09:00 | 2024-07-12 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2102 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Glenapp | Nammoona | Main Line, Loop Line | 2024-07-12 11:00 | 2024-07-12 18:00 | 7:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | GP8 to 104 | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-1873 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 2 | Total Possession | Mile End | Islington | Main Line | 2024-07-12 13:00 | 2024-07-13 01:30 | 12:30 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period - Was June | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-2969 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 3 | Total Possession | Islington | Dry Creek | Main Line | 2024-07-12 16:00 | 2024-07-12 23:00 | 7:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Adhoc Traffic - All Services Operate Under Train Order Working | Bryce Gore | Michael Iannella | Signal 1 Mile End to Signal 30 Islington |  | 2024-05-27
IPR-2910 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 3 | Total Possession | Mile End | Islington | Main Line | 2024-07-13 01:30 | 2024-07-13 11:30 | 10:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Adhoc Traffic - All Services Operate Under Train Order Working | Bryce Gore | Michael Iannella | Signal 1 Mile End to Signal 30 Islington |  | 2024-05-27
IPR-1790 | 2023-11-24 | Supported | 0820-2024 |  | 1 | Config 10-B | Port Botany Yard | Chullora Jct | All Lines | 2024-07-13 02:00 | 2024-07-15 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 B Possession (WE02) Chullora Junction North Fork Open, Flemington Goods Open, Sefton Junction Closed. SSFL Open | Shannon James | Warren Williams |  | LPA | 2023-11-15
IPR-2848 | 2024-05-23 | Approved | 0910-2024 | 2024-06-20 | 3 | Window Possession | Bogan Gate | Goobang Jct | Single Main | 2024-07-13 07:00 | 2024-07-13 19:00 | 12:00 | Resurfacing | North - South | Goobang Junction to Broken Hill |  | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2811 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-13 08:00 | 2024-07-13 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2103 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Kyogle | Grafton | Main Line, Loop Line | 2024-07-13 10:00 | 2024-07-13 16:00 | 6:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | KE1 to 45-4 | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-1860 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 2 | Total Possession | Mile End | Islington | Main Line | 2024-07-13 11:30 | 2024-07-13 23:30 | 12:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period - Was June | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-1986 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-07-14 00:05 | 2024-07-14 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2104 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Lawrence Road | Glenreagh | Main Line, Loop Line | 2024-07-14 06:30 | 2024-07-14 14:30 | 8:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 47 11M and 47 11L to 41-4 | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2849 | 2024-05-23 | Approved | 0911-2024 | 2024-06-20 | 3 | Window Possession | Cootamundra West | Goobang Jct | Single Main | 2024-07-14 07:00 | 2024-07-14 19:00 | 12:00 | Resurfacing | North - South | Cootamundra West to Goobang Junction | Working Parkes - Cootamundra West | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2812 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-14 08:00 | 2024-07-14 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2574 | 2023-11-24 | Cancelled |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-07-15 03:00 | 2024-07-15 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2024-03-21
IPR-2713 | 2023-11-24 | Cancelled |  |  | 1 | Total Possession | Benalla | Somerton | All Standard Gauge Tracks | 2024-07-15 05:00 | 2024-07-15 19:00 | 14:00 | Inland Rail & Other Major Works | North - South | Albury to Somerton | ​14 hour Occupation | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-2911 | 2024-06-24 | Approved | 0895-2024 | 2024-06-12 | 2 | Total Possession | Benalla | Chiltern | West Track | 2024-07-15 06:00 | 2024-07-15 16:00 | 10:00 | Turnout | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Peter Morgan |  |  | 2024-06-05
IPR-2105 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Grafton | Boambee Beach | Main Line, Loop Line | 2024-07-15 07:00 | 2024-07-15 15:00 | 8:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 45-4 to 37-3 | TOA | 2023-12-06
IPR-2850 | 2024-05-23 | Approved | 0911-2024 | 2024-06-20 | 3 | Window Possession | Cootamundra West | Goobang Jct | Single Main | 2024-07-15 07:00 | 2024-07-15 19:00 | 12:00 | Resurfacing | North - South | Cootamundra West to Goobang Junction | Working Parkes - Cootamundra West | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2813 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-15 08:00 | 2024-07-15 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2745 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-15 09:00 | 2024-07-15 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2926 | 2023-08-24 | Approved | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-07-15 16:00 | 2024-07-15 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2851 | 2024-05-23 | Approved | 0911-2024 | 2024-06-20 | 3 | Window Possession | Cootamundra West | Goobang Jct | Single Main | 2024-07-16 07:00 | 2024-07-16 19:00 | 12:00 | Resurfacing | North - South | Cootamundra West to Goobang Junction | Working Parkes - Cootamundra West | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2814 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-16 08:00 | 2024-07-16 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2106 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Nana Glen | Nambucca Heads | Main Line, Loop Line | 2024-07-16 09:00 | 2024-07-16 13:30 | 4:30 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 40-4 to 34-3 | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2747 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-16 09:00 | 2024-07-16 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2107 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Boambee Beach | Tamban | Main Line, Loop Line | 2024-07-17 05:30 | 2024-07-17 14:00 | 8:30 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 37-3 Signal to 31-3 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2852 | 2024-05-23 | Approved | 0911-2024 | 2024-06-20 | 3 | Window Possession | Cootamundra West | Goobang Jct | Single Main | 2024-07-17 07:00 | 2024-07-17 19:00 | 12:00 | Resurfacing | North - South | Cootamundra West to Goobang Junction | Working Parkes - Cootamundra West | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2815 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-17 08:00 | 2024-07-17 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2748 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-17 09:00 | 2024-07-17 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2609 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Parkes | Condobolin | Single Main | 2024-07-18 06:00 | 2024-07-18 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2108 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Nambucca Heads | Kundabung | Main Line, Loop Line | 2024-07-18 07:45 | 2024-07-18 17:45 | 10:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 34-3 Signal to 29-4 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2816 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-18 08:00 | 2024-07-18 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2749 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-18 09:00 | 2024-07-18 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | ​Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2610 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Condobolin | Euabalong West | Single Main | 2024-07-19 06:00 | 2024-07-19 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2750 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-19 09:00 | 2024-07-19 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2109 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Tamban | Johns River | Main Line, Loop Line | 2024-07-19 23:00 | 2024-07-20 03:00 | 4:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 31-3 Signal to 24-4 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2611 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Condobolin | Euabalong West | Single Main | 2024-07-20 06:00 | 2024-07-20 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2113 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Kerewong | Killawarra | Main Line, Loop Line | 2024-07-20 15:00 | 2024-07-20 20:00 | 5:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 26-4 Signal to 19-4 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-1987 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-07-21 00:05 | 2024-07-21 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2612 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Euabalong West | Trida | Single Main | 2024-07-21 06:00 | 2024-07-21 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2110 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Johns River | Bundook | Main Line, Loop Line | 2024-07-21 18:00 | 2024-07-22 05:00 | 11:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 24-3 Signal to 16-4 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2613 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Euabalong West | Trida | Single Main | 2024-07-22 06:00 | 2024-07-22 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2746 | 2022-12-21 | Cancelled | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | East Track | 2024-07-22 09:00 | 2024-07-22 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2927 | 2023-08-24 | Approved | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-07-22 16:00 | 2024-07-22 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2111 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Bundook | Gloucestor | Main Line, Loop Line | 2024-07-22 19:30 | 2024-07-23 02:00 | 6:30 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities (Possible Change to Day Shift - TBC) Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 16-3 Signal to 13-2 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresse - Working from Acacia Ridge in a Up direction towards Telarah - Possible change to day shift | 2023-12-06
IPR-2614 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Trida | Ivanhoe | Single Main | 2024-07-23 06:00 | 2024-07-23 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2853 | 2024-05-23 | Approved | 0912-2024 | 2024-06-20 | 3 | Window Possession | Ettamogah | The Rock | Single Main | 2024-07-23 07:00 | 2024-07-23 19:00 | 12:00 | Resurfacing | North - South | Junee to Albury |  | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2751 | 2022-12-21 | Cancelled | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | East Track | 2024-07-23 09:00 | 2024-07-23 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2112 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Mount George | Stroud Road | Main Line, Loop Line | 2024-07-23 20:30 | 2024-07-24 05:00 | 8:30 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 17-4 Signal to 09-4 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2615 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Trida | Ivanhoe | Single Main | 2024-07-24 06:00 | 2024-07-24 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2854 | 2024-05-23 | Approved | 0912-2024 | 2024-06-20 | 3 | Window Possession | Ettamogah | The Rock | Single Main | 2024-07-24 07:00 | 2024-07-24 19:00 | 12:00 | Resurfacing | North - South | Junee to Albury |  | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2752 | 2022-12-21 | Cancelled | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | East Track | 2024-07-24 09:00 | 2024-07-24 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2623 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Telarah | Dungog | Main Line and Crossing Loops | 2024-07-24 18:30 | 2024-07-25 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval,MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2908 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Gloucestor | Monkerai | Main Line, Loop Line | 2024-07-24 19:00 | 2024-07-25 05:00 | 10:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 13-2 Signal to 08-3 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2616 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Ivanhoe | Menindee | Single Main | 2024-07-25 06:00 | 2024-07-25 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2855 | 2024-05-23 | Approved | 0912-2024 | 2024-06-20 | 3 | Window Possession | The Rock | Wagga Wagga | Single Main | 2024-07-25 07:00 | 2024-07-25 19:00 | 12:00 | Resurfacing | North - South | Junee to Albury |  | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2624 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Dungog | Craven North | Main Line and Crossing Loops | 2024-07-25 18:30 | 2024-07-26 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2617 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Ivanhoe | Menindee | Single Main | 2024-07-26 06:00 | 2024-07-26 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2856 | 2024-05-23 | Approved | 0912-2024 | 2024-06-20 | 3 | Window Possession | Uranquinty | Junee | Single Main | 2024-07-26 07:00 | 2024-07-26 19:00 | 12:00 | Resurfacing | North - South | Junee to Albury |  | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2625 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Craven North | Mount George | Main Line and Crossing Loops | 2024-07-26 18:30 | 2024-07-27 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2080 | 2023-11-30 | Approved | 0892-2024 |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-07-27 06:00 | 2024-07-27 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 04 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2618 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Ivanhoe | Menindee | Single Main | 2024-07-27 06:00 | 2024-07-27 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2090 | 2023-11-30 | Approved | 0892-2024 |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-07-27 06:30 | 2024-07-27 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-2857 | 2024-05-23 | Approved | 0912-2024 | 2024-06-20 | 3 | Window Possession | Uranquinty | Junee | Single Main | 2024-07-27 07:00 | 2024-07-27 19:00 | 12:00 | Resurfacing | North - South | Junee to Albury |  | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2626 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Mount George | Taree | Main Line and Crossing Loops | 2024-07-27 18:30 | 2024-07-28 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-1988 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-07-28 00:05 | 2024-07-28 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2619 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Ivanhoe | Menindee | Single Main | 2024-07-28 06:00 | 2024-07-28 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2627 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Taree | Kendall | Main Line and Crossing Loops | 2024-07-28 18:30 | 2024-07-29 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2620 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Menindee | Broken Hill | Single Main | 2024-07-29 06:00 | 2024-07-29 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2872 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-29 09:00 | 2024-07-29 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2928 | 2023-08-24 | Approved | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-07-29 16:00 | 2024-07-29 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2628 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Kendall | Kundabung | Main Line and Crossing Loops | 2024-07-29 18:30 | 2024-07-30 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2621 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Menindee | Broken Hill | Single Main | 2024-07-30 06:00 | 2024-07-30 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2873 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-30 09:00 | 2024-07-30 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2629 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Taree | Kundabung | Main Line and Crossing Loops | 2024-07-30 18:30 | 2024-07-31 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2622 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Menindee | Broken Hill | Single Main | 2024-07-31 06:00 | 2024-07-31 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2874 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-31 09:00 | 2024-07-31 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2630 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Taree | Kundabung | Main | 2024-07-31 18:30 | 2024-08-01 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2776 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Menindee | Broken Hill | Single Main | 2024-08-01 06:00 | 2024-08-01 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2875 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-08-01 09:00 | 2024-08-01 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2876 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-08-02 09:00 | 2024-08-02 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2346 | 2024-02-26 | Supported | 0790-2024 |  | 1 | Total Possession | Flemington Goods Jct | Chullora Jct | Up and Down Goods Line | 2024-08-03 02:00 | 2024-08-05 02:00 | 48:00 | Sydney Trains Track Reconditioning & Rerailing | North - South | Sydney MFN | Adjoining Sydney Trains C9 Possession - Flemington Track Reconditioning & Re-Railing Down Enfield West Fork on Sydney Trains Side of Boundary Possession Down Enfield West Fork 19.84KMs to 20.300KMs of TAA Requested for 500 meters restriction of scope | Neil Doust | Jensen Kelly | Up Goods Clear of 347 Crossover to inclusive of ED 18.8 Signal (ST & ARTC Boundary) Down Goods - Clear of Signal ED 262D to Inclusive of ST 369 SJD (ST & ARTC Boundary) Chullora Junction Up North Fork - Clear of 351 Crossover to Inclusive of 348 Crossover | LPA | 2024-02-21
IPR-1797 | 2023-11-24 | Supported | 0789-2024 |  | 1 | Config 9 | Telarah | Taree | All Lines | 2024-08-03 03:00 | 2024-08-06 | 69:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Stage 1 - Telarah to Taree (Exclusive) | Neil Doust | Warren Williams | Telarah to Taree (Clear of Yard) | LPA | 2023-11-11
IPR-2492 | 2023-11-24 | Supported | 0789-2024 |  | 1 | Config 9 | Taree | Grafton City | All Lines | 2024-08-03 05:30 | 2024-08-05 19:00 | 61:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Stage 2 - Taree (Inclusive) to Grafton City (Exclusive) | Neil Doust | Warren Williams |  | LPA | 2023-11-11
IPR-2493 | 2023-11-24 | Supported | 0789-2024 |  | 1 | Config 9 | Grafton City | Casino | All Lines | 2024-08-03 05:30 | 2024-08-05 17:00 | 59:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Stage 3 - Grafton City (Inclusive) to Casino (Inclusive) | Neil Doust | Warren Williams |  | LPA | 2023-11-11
IPR-2494 | 2023-11-24 | Supported | 0789-2024 |  | 1 | Config 9 | Casino | Acacia Ridge | All Lines | 2024-08-03 05:30 | 2024-08-05 19:00 | 61:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Stage 4 - Casino (Exclusive) to Acacia Ridge (Exclusive) | Neil Doust | Warren Williams |  | LPA | 2023-11-11
IPR-1989 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-08-04 00:05 | 2024-08-04 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2929 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-08-05 16:00 | 2024-08-05 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2775 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Loadstone | Acacia Ridge | Main | 2024-08-06 06:00 | 2024-08-06 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2777 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Loadstone | Acacia Ridge | Main | 2024-08-07 06:00 | 2024-08-07 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2970 | 2024-06-24 | Approved |  |  | 3 | Total Possession | Mile End | Belair | Main Line | 2024-08-07 20:30 | 2024-08-08 05:00 | 8:30 | TRJ Project | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signals 4 & 4E Belair |  | 2024-06-21
IPR-2778 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Grafton | Loadstone | Main | 2024-08-08 06:00 | 2024-08-08 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2779 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Grafton | Loadstone | Main | 2024-08-09 06:00 | 2024-08-09 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2913 | 2024-03-25 | Approved | 0881-2024 | 2024-06-14 | 2 | Total Possession | Broken Hill | Broken Hill | Branch Line | 2024-08-09 06:00 | 2024-08-09 18:00 | 12:00 | Reconditioning Iodide St Lvl-X . Branch Line Track Replacement | East - West | Goobang Junction to Broken Hill | MANDATORY TRAINS AND ROAD TRAFFIC TO BE MANAGED . NO ADHOCS | Neil Doust | Bonnar Mahains
IPR-2755 | 2024-05-23 | Pending |  |  | 3 | Window Possession | Junee | Jindalee | Up Main | 2024-08-09 07:00 | 2024-08-09 17:00 | 10:00 | Rail Grinding | North - South |  | Rail Grinding on Up Main. PSW via Down Main. Alterations to mandatories. | Andrew Duncan | Owen Blake |  |  | 2024-05-06
IPR-2780 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Grafton | Loadstone | Main | 2024-08-10 06:00 | 2024-08-10 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2914 | 2024-03-25 | Approved | 0881-2024 | 2024-06-14 | 2 | Total Possession | Broken Hill | Broken Hill | Main Line | 2024-08-10 06:00 | 2024-08-10 18:00 | 12:00 | Reconditioning Iodide St Lvl-X . Main Line Track Replacement | East - West | Goobang Junction to Broken Hill | MANDATORY TRAINS AND ROAD TRAFFIC TO BE MANAGED . NO ADHOCS | Neil Doust | Bonnar Mahains
IPR-2756 | 2024-05-23 | Pending |  |  | 3 | Window Possession | Junee | Jindalee | Up Main | 2024-08-10 07:00 | 2024-08-10 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Up Main. PSW via Down Main. | Andrew Duncan | Owen Blake |  |  | 2024-05-06
IPR-1990 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-08-11 00:05 | 2024-08-11 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2781 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Lawrence Road | Grafton | Main | 2024-08-11 06:00 | 2024-08-11 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2757 | 2024-05-23 | Pending |  |  | 3 | Window Possession | Jindalee | Junee | Down Main | 2024-08-11 07:00 | 2024-08-11 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Down Main. PSW via Up Main. Alterations to mandatories. | Andrew Duncan | Owen Blake |  |  | 2024-05-06
IPR-2782 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Lawrence Road | Grafton | Main | 2024-08-12 06:00 | 2024-08-12 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2915 | 2024-03-25 | Approved | 0881-2024 | 2024-06-14 | 2 | Total Possession | Broken Hill | Broken Hill | Main & Branch Lines | 2024-08-12 06:00 | 2024-08-12 14:00 | 8:00 | Reconditioning Iodide St Lvl-X . Asphalting. | East - West | Goobang Junction to Broken Hill | MANDATORY TRAINS AND ROAD TRAFFIC TO BE MANAGED . NO ADHOCS | Neil Doust | Bonnar Mahains
IPR-2758 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Jindalee | Harden | Up Main | 2024-08-12 07:00 | 2024-08-12 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Up Main. PSW via Down Main. Alterations to mandatories. | Andrew Duncan | Owen Blake | Jindalee CA05 Signal to Harden HN28 Signal |  | 2024-05-06
IPR-2930 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-08-12 16:00 | 2024-08-12 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2759 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Harden | Jindalee | Down Main | 2024-08-13 07:00 | 2024-08-13 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Down Main. PSW via Up Main. Alterations to mandatories. | Andrew Duncan | Owen Blake | Harden Clr of 105pts to Jindalee CA03 Signal |  | 2024-05-06
IPR-2689 | 2024-04-23 | Pending |  |  | 2 | Total Possession | Berrybank Loop | Tooli Loop | Mainline | 2024-08-14 06:00 | 2024-08-14 18:00 | 12:00 | Re-Railing | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Derek Rowan |  |  | 2024-04-15
IPR-2760 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Harden | Yass Jct | Up Main | 2024-08-14 07:00 | 2024-08-14 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Up Main. PSW via Down Main. Alterations to mandatories. | Andrew Duncan | Owen Blake | Harden Clr of 105pts to Yass Junction YJ24 Signal |  | 2024-05-06
IPR-2971 | 2024-06-24 | Approved |  |  | 3 | Total Possession | Mile End | Belair | Main Line | 2024-08-14 20:30 | 2024-08-15 05:00 | 8:30 | TRJ Project | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signals 4 & 4E Belair |  | 2024-06-21
IPR-2690 | 2024-04-23 | Pending |  |  | 2 | Total Possession | Berrybank Loop | Tooli Loop | Mainline | 2024-08-15 06:00 | 2024-08-15 18:00 | 12:00 | Re-Railing | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Derek Rowan |  |  | 2024-04-15
IPR-2761 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Yass Jct | Galong | Down Main | 2024-08-15 07:00 | 2024-08-15 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Down Main. PSW via Up Main. Alterations to mandatories. | Andrew Duncan | Owen Blake | Yass Junction YJ18 Signal to Galong 364.9 Signal |  | 2024-05-06
IPR-2762 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Galong | Harden | Down Main | 2024-08-16 07:00 | 2024-08-16 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Down Main. PSW via Up Main. Alterations to mandatories. | Andrew Duncan | Owen Blake | Galong 364.9 Signal to Harden HN15 Signal |  | 2024-05-06
IPR-2081 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-08-17 06:00 | 2024-08-17 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 07 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2091 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-08-17 06:30 | 2024-08-17 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1991 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-08-18 00:05 | 2024-08-18 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2931 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-08-19 16:00 | 2024-08-19 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2468 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Tent Hill | McLeay | Main Line & Loops | 2024-08-20 13:30 | 2024-08-21 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2783 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Glenreagh | Lawrence Road | Main | 2024-08-21 06:00 | 2024-08-21 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2784 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Glenreagh | Lawrence Road | Main | 2024-08-22 06:00 | 2024-08-22 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2785 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Boambee Beach | Glenreagh | Main | 2024-08-23 06:00 | 2024-08-23 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2786 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Boambee Beach | Glenreagh | Main | 2024-08-24 06:00 | 2024-08-24 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2789 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Albury | The Rock | Main | 2024-08-24 06:00 | 2024-08-24 18:00 | 12:00 | Ultrasonic Testing | North - South | Junee to Albury | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-05-10
IPR-1992 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-08-25 00:05 | 2024-08-25 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2787 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Eungai | Boambee Beach | Main | 2024-08-25 06:00 | 2024-08-25 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2790 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Albury | The Rock | Main | 2024-08-25 06:00 | 2024-08-25 18:00 | 12:00 | Ultrasonic Testing | North - South | Junee to Albury | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-05-10
IPR-2788 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Eungai | Boambee Beach | Main | 2024-08-26 06:00 | 2024-08-26 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2791 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Albury | The Rock | Main | 2024-08-26 06:00 | 2024-08-26 18:00 | 12:00 | Ultrasonic Testing | North - South | Junee to Albury | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-05-10
IPR-2932 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-08-26 16:00 | 2024-08-26 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2792 | 2024-05-23 | Supported |  |  | 3 | Window Possession | The Rock | Junee | Main | 2024-08-27 06:00 | 2024-08-27 18:00 | 12:00 | Ultrasonic Testing | North - South | Junee to Albury | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-05-10
IPR-2919 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Eungai | Kundabung | Main | 2024-08-27 06:00 | 2024-08-27 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2127 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Spencer Jct | Tarcoola | Main Line & Loops | 2024-08-27 13:30 | 2024-08-28 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required Reduced down from initial 36hr request | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2793 | 2024-05-23 | Supported |  |  | 3 | Window Possession | The Rock | Junee | Main | 2024-08-28 06:00 | 2024-08-28 18:00 | 12:00 | Ultrasonic Testing | North - South | Junee to Albury | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-05-10
IPR-2794 | 2024-05-23 | Supported |  |  | 3 | Window Possession | The Rock | Junee | Main | 2024-08-29 06:00 | 2024-08-29 18:00 | 12:00 | Ultrasonic Testing | North - South | Junee to Albury | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-05-10
IPR-2700 | 2024-04-23 | Pending |  |  | 1 | Total Possession | Birkenhead | Outer Harbor | All Lines | 2024-08-31 06:00 | 2024-09-01 22:00 | 40:00 | SAPN Power Supply | East - West | Outer Harbour Line | No Train Period | Bryce Gore | Darren Schulz |  |  | 2024-04-22
IPR-2763 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Yass Jct | Joppa Jct | Up Main | 2024-08-31 07:00 | 2024-08-31 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Up Main. PSW via Down Main. Mandatories affected. | Andrew Duncan | Owen Blake | Yass Junction YJ7 Signal to Joppa Junction G4 Signal |  | 2024-05-06
IPR-2644 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Cooks River | Enfield | Down Goods | 2024-10-19 08:00 | 2024-10-19 18:00 | 10:00 | Sydney Metro Construction Activities | North - South | Sydney MFN | Possession of the Down Goods between Cooks River & Enfield. Clear of Cooks River & Enfield Yards. NO Access from the Illawarra Lines Botany to Cooks River Remains OPEN. Impacts to: 1155 (PN), 1297 (PN), 1902 (RC), 9138 (PN), 1157 (PN), 1293 (PN). | Shannon James | Steven Payne |  | LPA | 2024-04-10
IPR-2648 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-10-19 08:00 | 2024-10-19 11:30 | 3:30 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open.Impacted Services: 1152 (PN), 2192 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2652 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-10-19 15:00 | 2024-10-19 18:00 | 3:00 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 2196 (PN), 1156 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-1993 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-09-01 00:05 | 2024-09-01 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2764 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Yass Jct | Joppa Jct | Up Main | 2024-09-01 07:00 | 2024-09-01 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Up Main. PSW via Down Main. Mandatories affected. | Andrew Duncan | Owen Blake | Yass Junction YJ7 Signal to Joppa Junction G4 Signal |  | 2024-05-06
IPR-2645 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Cooks River | Enfield | Down Goods | 2024-10-20 08:00 | 2024-10-20 18:00 | 10:00 | Sydney Metro Construction Activities | North - South | Sydney MFN | Possession of the Down Goods between Cooks River & Enfield. Clear of Cooks River & Enfield Yards. NO Access from the Illawarra Lines Botany to Cooks River Remains OPEN. Impacts to: 1297 (PN), 1155 (PN), 9102 (RC), 9138 (PN), 1157 (PN), 1293 (PN) | Shannon James | Steven Payne |  | LPA | 2024-04-10
IPR-2649 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-10-20 08:00 | 2024-10-20 11:30 | 3:30 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 1152 (PN), 2192 (PN), 1907 (RC), 2196 (PN) In conjunction with Down Goods LPA Handback window from 1130 to 1500 | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2653 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-10-20 15:00 | 2024-10-20 18:00 | 3:00 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 1156 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2765 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Joppa Jct | Yass Jct | Down Main | 2024-09-02 07:00 | 2024-09-02 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Down Main. PSW via Up Main. Mandatories affected. | Andrew Duncan | Owen Blake | Goulburn Clr of 101pts to Yass Junction YJ5 Signal |  | 2024-05-06
IPR-2933 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-09-02 16:00 | 2024-09-02 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2766 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Goulburn | Lynwood | Up Main | 2024-09-03 07:00 | 2024-09-03 17:00 | 10:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Up Main. PSW via Down Main. Mandatories affected. | Andrew Duncan | Owen Blake | Goulburn G78 Signal to Lynwood LD14 Signal |  | 2024-05-06
IPR-2124 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Coondambo | Tarcoola | Main Line & Loops | 2024-09-03 13:30 | 2024-09-04 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2767 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Marulan | Goulburn | Down Main | 2024-09-04 07:00 | 2024-09-04 17:00 | 10:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Down Main. PSW via Up Main. Mandatories affected. | Andrew Duncan | Owen Blake | Marulan Clr of E Frame to Goulburn G75 Signal |  | 2024-05-06
IPR-2768 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Marulan | Wingello | Up Main | 2024-09-05 07:00 | 2024-09-05 17:00 | 10:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Up Main. PSW via Down Main. Mandatories affected. | Andrew Duncan | Owen Blake | Wingello Clr of C Frame to Marulan Clr of E Frame |  | 2024-05-06
IPR-1794 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2024-09-07 01:00 | 2024-09-08 23:00 | 46:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN | Shannon James | Warren Williams |  | LPA | 2023-11-10
IPR-2082 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-09-07 06:00 | 2024-09-07 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 10 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) In alignment with Config 16 | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2092 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-09-07 06:30 | 2024-09-07 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line In Alignment with Config 16 | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1994 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-09-08 00:05 | 2024-09-08 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2934 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-09-09 16:00 | 2024-09-09 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2769 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Wingello | Marulan | Down Main | 2024-09-10 07:00 | 2024-09-10 17:00 | 10:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Down Main. PSW via Up Main. Mandatories affected. | Andrew Duncan | Owen Blake | Wingello Clr of D Frame to Marulan Clr of D Frame |  | 2024-05-06
IPR-2125 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Wirrappa | Pimba | Main Line & Loops | 2024-09-10 13:30 | 2024-09-11 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2770 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Wingello | Moss Vale | Up Main | 2024-09-11 18:00 | 2024-09-12 06:00 | 12:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Up Main. PSW via Down Main. Mandatories affected. | Andrew Duncan | Owen Blake | Wingello Clr of D Frame to Moss Vale MV88 Signal |  | 2024-05-06
IPR-1801 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Junction | SSFL, Up Main, Down Main | 2024-09-13 22:30 | 2024-09-16 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. | Neil Doust | Warren Williams |  | LPA | 2023-11-10
IPR-1807 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Moss Vale | Goulburn | All Lines | 2024-09-14 00:01 | 2024-09-16 18:00 | 65:59 | Major Maintenance, SHOO Project Construction | North - South | Moss Vale to Goulburn | ARTC South 'Super' Possession, Aligned with Config 14. | Neil Doust | Warren Williams | Moss Vale Yard (Exclusive) to Goulburn Yard (Inclusive) | LPA | 2023-11-10
IPR-2237 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Junction | Moss Vale | All Lines | 2024-09-14 00:01 | 2024-09-16 02:00 | 49:59 | Major Maintenance | North - South | Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. | Neil Doust | Warren Williams |  | LPA | 2023-11-10
IPR-1808 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Goulburn | Albury | All Lines | 2024-09-14 03:00 | 2024-09-16 18:00 | 63:00 | Major Maintenance | North - South | Goulburn to Junee;#Junee to Albury | Aligned with ARTC Config 14 | Neil Doust | Warren Williams | Goulburn Yard (Exclusive) to Albury (Inclusive) | LPA | 2023-11-10
IPR-1811 | 2023-11-24 | Approved |  |  | 1 | North-East Vic 'Super' Possession | Albury | Somerton | All Lines | 2024-09-14 06:00 | 2024-09-16 18:00 | 60:00 | Major Maintenance | North - South | Albury to Somerton | Aligned with ARTC Config 14 & South 'Super' Shut | Neil Doust | Warren Williams | Albury (Exclusive) to Somerton (Inclusive) | AO | 2023-11-10
IPR-1813 | 2023-11-24 | Approved |  |  | 1 | North-East Vic 'Super' Possession | Somerton | Tottenham | All ARTC Lines, Including DG & BG Lines | 2024-09-14 06:00 | 2024-09-16 18:00 | 60:00 | Major Maintenance | East - West | Somerton to Tottenham Jct;#Albion to Jacana Broad Gauge | Aligned with ARTC Config 14 & South 'Super' Shut | Neil Doust | Warren Williams | Somerton (Exclusive) to Tottenham (Exclusive) | AO | 2023-11-10
IPR-2430 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Cootamundra West | Forbes | All Lines | 2024-09-14 06:00 | 2024-09-16 18:00 | 60:00 | Major Maintenance | North - South | Cootamundra West to Goobang Junction | Aligned with ARTC Config 14 | Neil Doust | Warren Williams | Cootamundra West (Inclusive) to Goobang Junction (Exclusive) | TOA | 2023-11-10
IPR-2656 | 2024-05-23 | Supported | 0935-2024 |  | 1 | Total Possession | Forbes | Goobang Jct | Main Line | 2024-09-14 06:00 | 2024-09-18 10:00 | 100:00 | Inland Rail Construction Activities | North - South | Cootamundra West to Goobang Junction | WYNDHAM AVE BRIDGE Earthworks, piling & drainage DAROOBALGIE CROSSING LOOP Turnout Construction works | Andrew Duncan | Chris Fay | Forbes DYLB to GJ124 | LPA | 2024-04-05
IPR-2646 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Cooks River | Enfield | Down Goods | 2024-11-02 08:00 | 2024-11-02 18:00 | 10:00 | Sydney Metro Construction Activities | North - South | Sydney MFN | Possession of the Down Goods between Cooks River & Enfield. Clear of Cooks River & Enfield Yards. NO Access from the Illawarra Lines Botany to Cooks River Remains OPEN. Impacts to: 1155 (PN), 1297 (PN), 1902 (RC), 9138 (PN), 1157 (PN), 1293 (PN). | Shannon James | Steven Payne |  | LPA | 2024-04-10
IPR-2650 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-11-02 08:00 | 2024-11-02 11:30 | 3:30 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open.Impacted Services: 1152 (PN), 2192 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2654 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-11-02 15:00 | 2024-11-02 18:00 | 3:00 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 2196 (PN), 1156 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-1995 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-09-15 00:05 | 2024-09-15 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2647 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Cooks River | Enfield | Down Goods | 2024-11-03 08:00 | 2024-11-03 18:00 | 10:00 | Sydney Metro Construction Activities | North - South | Sydney MFN | Possession of the Down Goods between Cooks River & Enfield. Clear of Cooks River & Enfield Yards. NO Access from the Illawarra Lines Botany to Cooks River Remains OPEN. Impacts to: 1297 (PN), 1155 (PN), 9102 (RC), 9138 (PN), 1157 (PN), 1293 (PN) | Shannon James | Steven Payne |  | LPA | 2024-04-10
IPR-2651 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-11-03 08:00 | 2024-11-03 11:30 | 3:30 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 1152 (PN), 2192 (PN), 1907 (RC), 2196 (PN) In conjunction with Down Goods LPA Handback window from 1130 to 1500 | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2655 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-11-03 15:00 | 2024-11-03 18:00 | 3:00 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 1156 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2935 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-09-16 16:00 | 2024-09-16 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2126 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Pimba | Burando | Main Line & Loops | 2024-09-17 13:30 | 2024-09-18 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works (Contingency Possession) Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2771 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Moss Vale | Wingello | Down Main | 2024-09-17 18:00 | 2024-09-18 06:00 | 12:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Down Main. PSW via Up Main. Mandatories affected. | Andrew Duncan | Owen Blake | Moss Vale MV79 Signal to Wingello Clr of C Frame |  | 2024-05-06
IPR-2772 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Goulburn | Joppa Jct | Up Main | 2024-09-18 18:00 | 2024-09-19 06:00 | 12:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Up Main. PSW via Down Main. Mandatories affected. | Andrew Duncan | Owen Blake | Within Goulburn Yard Limits |  | 2024-05-06
IPR-2773 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Joppa Jct | Goulburn | Down Main | 2024-09-19 18:00 | 2024-09-20 06:00 | 12:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Down Main. PSW via Up Main. Mandatories affected. | Andrew Duncan | Owen Blake | Within Goulburn Yard Limits |  | 2024-05-06
IPR-1996 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-09-22 00:05 | 2024-09-22 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2936 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-09-23 16:00 | 2024-09-23 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2469 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Pimba | Burando | Main Line & Loops | 2024-09-24 13:30 | 2024-09-25 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works (Contingency Possession) Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-1997 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-09-29 00:05 | 2024-09-29 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1874 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Mile End | Islington | Main Line | 2024-09-30 00:01 | 2024-10-02 18:30 | 66:29 | TRJ Project Commissioning | East - West | Serviceton to Islington (SA) | ​Torrens Junction Signalling Upgrade Project - IP's & Ghan to be programmed through works | Bryce Gore | Michael Iannella | Islington Signals 32 & 34 to Mile End Signals 43, 45 & 45E |  | 2023-11-21
IPR-2963 | 2024-06-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-09-30 06:00 | 2024-10-02 06:00 | 48:00 | Underbridge Replacement 165.549km | East - West | Dry Creek to Crystal Brook | As large a windows as possible aligning with East - West Shut. Minimum 14hr No Train Period with smaller follow up window | Shannon James | Kristen Xiao | Signal 24 Snowtown to Signal 3 Redhill |  | 2024-06-21
IPR-1894 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Manor Loop | Serviceton | All Tracks | 2024-09-30 06:30 | 2024-10-02 18:30 | 60:00 | Major Maintenance | East - West | Tottenham to Serviceton | ​​Major Maintenance being conducted. Timing of Stages TBC. | Bryce Gore | Bryce Gore |  |  | 2023-11-21
IPR-1895 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Serviceton | Mile End | All Tracks | 2024-09-30 06:30 | 2024-10-02 18:30 | 60:00 | Major Maintenance | East - West | Serviceton to Islington (SA) | ​​Major Maintenance being conducted.Timing of Stages TBC. | Bryce Gore | Bryce Gore |  |  | 2023-11-21
IPR-2937 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-09-30 16:00 | 2024-09-30 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2121 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Spencer Jct | Tent Hill | Main Line & Loops | 2024-10-01 13:30 | 2024-10-02 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-1998 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-10-06 00:05 | 2024-10-06 07:00 | 6:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2900 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wallan | Wallan | Mainline | 2024-10-07 06:00 | 2024-10-11 18:00 | 108:00 | Inland Rail Track Slew | North - South | Albury to Somerton | All Services Operate Via Crossing Loop | Bryce Gore | Tanishq Sarkar |  |  | 2024-05-27
IPR-2877 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-07 09:00 | 2024-10-07 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2938 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-10-07 17:00 | 2024-10-07 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2878 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-08 09:00 | 2024-10-08 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2122 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Spencer Jct | Tent Hill | Main Line & Loops | 2024-10-08 15:00 | 2024-10-09 04:00 | 13:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2879 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-09 09:00 | 2024-10-09 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2880 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-10 09:00 | 2024-10-10 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2881 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-11 09:00 | 2024-10-11 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2083 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-10-12 06:00 | 2024-10-12 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 16 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2093 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-10-12 06:30 | 2024-10-12 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1999 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-10-13 00:05 | 2024-10-13 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2882 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-14 09:00 | 2024-10-14 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2939 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-10-14 17:00 | 2024-10-14 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2883 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-15 09:00 | 2024-10-15 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2123 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Tent Hill | McLeay | Main Line & Loops | 2024-10-15 13:30 | 2024-10-16 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2884 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-16 09:00 | 2024-10-16 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2885 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-17 09:00 | 2024-10-17 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2886 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-18 09:00 | 2024-10-18 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2000 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-10-20 00:05 | 2024-10-20 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1973 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-10-21 03:00 | 2024-10-21 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track - was 9th September | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-2912 | 2024-06-24 | Pending |  |  | 1 | Total Possession | Seymour | Longwood | All Tracks | 2024-10-21 06:00 | 2024-10-21 18:00 | 12:00 | Inland Rail - Seymour - Major Works | North - South | Albury to Somerton | ​12 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2024-06-06
IPR-2887 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-21 09:00 | 2024-10-21 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2940 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-10-21 17:00 | 2024-10-21 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2888 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-22 09:00 | 2024-10-22 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2889 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-23 09:00 | 2024-10-23 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2890 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-24 09:00 | 2024-10-24 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2891 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-25 09:00 | 2024-10-25 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2001 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-10-27 00:05 | 2024-10-27 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2921 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Benalla | All Tracks | 2024-10-28 03:00 | 2024-10-28 21:00 | 18:00 | Glenrowan Bridge Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-2941 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-10-28 17:00 | 2024-10-28 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2495 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Taree | Grafton City | All Lines | 2024-11-02 05:00 | 2024-11-03 19:30 | 38:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Taree (Inclusive) to Grafton City (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2496 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Grafton City | Casino | All Lines | 2024-11-02 05:30 | 2024-11-03 17:00 | 35:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Grafton City (Inclusive) to Casino (Inclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2084 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-11-02 06:00 | 2024-11-02 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 18 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) In alignment with Config 9 | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2094 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-11-02 06:30 | 2024-11-02 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1798 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Taree | All Lines | 2024-11-02 07:00 | 2024-11-04 01:00 | 42:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Telarah to Taree (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2497 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Casino | Acacia Ridge | All Lines | 2024-11-02 07:00 | 2024-11-03 18:00 | 35:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Casino (Exclusive) to Acacia Ridge (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2964 | 2024-06-24 | Pending |  |  | 2 | Total Possession | Snowtown | Snowtown | Mainline & Loop | 2024-11-02 21:00 | 2024-11-03 11:00 | 14:00 | Underbridge Replacement 144km | East - West | Dry Creek to Crystal Brook | No Train Period | Shannon James | Kristen Xiao | Signals 3 to 24 Snowtown |  | 2024-06-21
IPR-2002 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-11-03 00:05 | 2024-11-03 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2965 | 2024-06-24 | Pending |  |  | 3 | Total Possession | Snowtown | Snowtown | Mainline & Loop | 2024-11-03 22:00 | 2024-11-04 09:30 | 11:30 | Underbridge Replacement 144km | East - West | Dry Creek to Crystal Brook | No Train Period | Shannon James | Kristen Xiao | Signals 3 to 24 Snowtown |  | 2024-06-21
IPR-2942 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-11-04 17:00 | 2024-11-04 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2966 | 2024-06-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-11-09 21:00 | 2024-11-10 11:00 | 14:00 | Underbridge Replacement 148.738km | East - West | Dry Creek to Crystal Brook | No Train Period | Shannon James | Kristen Xiao | Signal 24 Snowtown to Signal 3 Redhill |  | 2024-06-21
IPR-2003 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-11-10 00:05 | 2024-11-10 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2967 | 2024-06-24 | Pending |  |  | 3 | Total Possession | Snowtown | Redhill | Mainline | 2024-11-10 22:00 | 2024-11-11 09:30 | 11:30 | Underbridge Replacement 148.738km | East - West | Dry Creek to Crystal Brook | No Train Period | Shannon James | Kristen Xiao | Signal 24 Snowtown to Signal 3 Redhill |  | 2024-06-21
IPR-2943 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-11-11 17:00 | 2024-11-11 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2004 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-11-17 00:05 | 2024-11-17 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2944 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-11-18 17:00 | 2024-11-18 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-1802 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Junction | SSFL, Up Main, Down Main | 2024-11-22 22:30 | 2024-11-25 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. | Andrew Duncan | Warren Williams |  | LPA | 2023-11-10
IPR-1806 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Junction | Cootamundra | All Lines | 2024-11-23 06:00 | 2024-11-24 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Goulburn;#Goulburn to Junee | Extended Config 14 Possession Moss Vale (Inclusive) to Cootamundra (Exclusive). Access Open to Cootamundra West from Cootamundra Yard | Andrew Duncan | Warren Williams |  | LPA | 2023-11-10
IPR-2005 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-11-24 00:05 | 2024-11-24 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1795 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2024-11-30 01:00 | 2024-12-01 23:00 | 46:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN. (WE22) | Neil Doust | Warren Williams |  | LPA | 2023-11-10
IPR-2924 | 2024-06-24 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | All Lines | 2024-11-30 23:00 | 2024-12-01 08:00 | 9:00 | SCU Project | North - South | Albury to Somerton | No Train Period | Bryce Gore | Thiago Cavalcanti |  |  | 2024-06-05
IPR-2006 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-12-01 00:05 | 2024-12-01 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1792 | 2023-11-24 | Supported |  |  | 1 | Config 10-A | Port Botany Yard | Flemington Goods Jct | All Lines | 2024-12-07 02:00 | 2024-12-09 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 A Possession (WE23) Flemington Goods Closed, Sefton Junction Open into SOY. SSFL Open | Shannon James | Warren Williams |  | LPA | 2023-11-15
IPR-2007 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-12-08 00:05 | 2024-12-08 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2085 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-12-14 06:00 | 2024-12-14 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 24 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2095 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-12-14 06:30 | 2024-12-14 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-2008 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-12-15 00:05 | 2024-12-15 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2009 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-12-22 00:05 | 2024-12-22 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2010 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-12-29 00:05 | 2024-12-29 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2858 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2025-01-18 06:00 | 2025-01-18 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 29 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2859 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2025-01-18 06:30 | 2025-01-18 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-2503 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Taree | Grafton City | All Lines | 2025-02-08 05:00 | 2025-02-09 19:30 | 38:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Taree (Inclusive) to Grafton City (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2500 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Grafton City | Casino | All Lines | 2025-02-08 05:30 | 2025-02-09 17:00 | 35:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Grafton City (Inclusive) to Casino (Inclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2860 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2025-02-08 06:00 | 2025-02-08 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 32- Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2861 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2025-02-08 06:30 | 2025-02-08 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1799 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Taree | All Lines | 2025-02-08 07:00 | 2025-02-10 01:00 | 42:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Telarah to Taree (Exclusive) | Andrew Duncan | Warren Williams |  | LPA | 2023-11-11
IPR-2499 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Casino | Acacia Ridge | All Lines | 2025-02-08 07:00 | 2025-02-09 18:00 | 35:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Casino (Exclusive) to Acacia Ridge (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2871 | 2024-05-23 | Pending |  |  | 1 | Total Possession | Condobolin | Goobang Jct | All Lines | 2025-02-22 06:00 | 2025-02-24 18:00 | 60:00 | Multiple Culvert Replacements | East - West | Goobang Junction to Broken Hill | 60hr Total Track Closure.Dates & Times may be refined | Andrew Duncan | Simon Bower |  |  | 2024-05-23
IPR-2829 | 2022-12-21 | Pending |  | 2024-05-02 | 2 | Total Possession | Benalla | Violet Town | West Track | 2025-03-03 06:00 | 2025-03-05 18:00 | 60:00 | Bridge Deck Renewals at 5 Sites | North - South | Albury to Somerton | ​​SLR on East Track | Bryce Gore | William Miholos |  |  | 2024-05-17
IPR-2841 | 2022-12-21 | Pending |  | 2024-05-02 | 2 | Total Possession | Benalla | Violet Town | West Track | 2025-03-06 06:00 | 2025-03-08 18:00 | 60:00 | Bridge Deck Renewals at 5 Sites | North - South | Albury to Somerton | ​​SLR on East Track | Bryce Gore | William Miholos |  |  | 2024-05-17
IPR-2862 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2025-03-08 06:00 | 2025-03-08 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 36- Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2864 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2025-03-08 06:30 | 2025-03-08 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1803 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Junction | SSFL, Up Main, Down Main | 2025-03-21 22:30 | 2025-03-24 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains (WE38) | Shannon James | Warren Williams |  | LPA | 2023-11-10
IPR-1810 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Moss Vale | Goulburn | All Lines | 2025-03-22 00:01 | 2025-03-24 18:00 | 65:59 | Major Maintenance, SHOO Project Construction | North - South | Moss Vale to Goulburn | ARTC South 'Super' Possession, Aligned with Config 14. | Shannon James | Warren Williams | Moss Vale Yard (Exclusive) to Goulburn Yard (Inclusive) | LPA | 2023-11-10
IPR-2238 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Junction | Moss Vale | All Lines | 2025-03-22 00:01 | 2025-03-24 02:00 | 49:59 | Major Maintenance | North - South | Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. | Neil Doust | Warren Williams |  | LPA | 2023-11-10
IPR-1809 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Goulburn | Albury | All Lines | 2025-03-22 03:00 | 2025-03-24 18:00 | 63:00 | Major Maintenance | North - South | Goulburn to Junee;#Junee to Albury | Aligned with ARTC Config 14 | Shannon James | Warren Williams | Goulburn Yard (Exclusive) to Albury (Inclusive) | LPA | 2023-11-10
IPR-1812 | 2023-11-24 | Approved |  |  | 1 | North-East Vic 'Super' Possession | Albury | Somerton | All Lines | 2025-03-22 06:00 | 2025-03-24 18:00 | 60:00 | Major Maintenance | North - South | Albury to Somerton | Aligned with ARTC Config 14 & South 'Super' Possession | Shannon James | Warren Williams | Albury (Exclusive) to Somerton (Inclusive) | AO | 2023-11-10
IPR-1814 | 2023-11-24 | Approved |  |  | 1 | North-East Vic 'Super' Possession | Somerton | Tottenham | All ARTC Lines, Including DG & BG Lines | 2025-03-22 06:00 | 2025-03-24 18:00 | 60:00 | Major Maintenance | East - West | Somerton to Tottenham Jct;#Albion to Jacana Broad Gauge | Aligned with ARTC Config 14 & South 'Super' Possession | Shannon James | Warren Williams | Somerton (Exclusive) | AO | 2023-11-10
IPR-2431 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Cootamundra West | Goobang Jct | All Lines | 2025-03-22 06:00 | 2025-03-24 18:00 | 60:00 | Major Maintenance | North - South | Cootamundra West to Goobang Junction | Aligned with ARTC Config 14 | Neil Doust | Warren Williams | Cootamundra West (Inclusive) to Goobang Junction (Exclusive) | TOA | 2023-11-10
IPR-1791 | 2023-11-24 | Supported |  |  | 1 | Config 10-B | Port Botany Yard | Chullora Jct | All Lines | 2025-03-29 02:00 | 2025-03-31 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 B Possession.Chullora Junction North Fork Open, Flemington Goods Open, Sefton Junction Closed. SSFL Open | Neil Doust | Warren Williams |  | LPA | 2023-11-15
IPR-1796 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2025-04-12 01:00 | 2025-04-13 23:00 | 46:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN | Andrew Duncan | Warren Williams |  | LPA | 2023-11-10
IPR-2863 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2025-04-12 05:00 | 2025-04-12 15:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 41- Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2865 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2025-04-12 05:30 | 2025-04-12 15:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-2870 | 2024-05-23 | Pending |  |  | 1 | Total Possession | Bolivar | Crystal Brook | Main | 2025-04-23 18:00 | 2025-04-26 06:00 | 60:00 | Light River Bridge Replacement | East - West | Dry Creek to Crystal Brook | Bridge Replacement - 60hr Track Closure | Bryce Gore | Kristen Xiao |  |  | 2024-05-23
IPR-2968 | 2024-06-24 | Pending |  |  | 1 | Total Possession | Snowtown | Redhill | Mainline | 2025-04-23 18:00 | 2025-04-26 06:00 | 60:00 | Underbridge Replacement 149.945 | East - West | Dry Creek to Crystal Brook | Aligns with Light River Bridge Replacement - 60hr Track Closure | Shannon James | Kristen Xiao | Signal 24 Snowtown to Signal 3 Redhill |  | 2024-06-21
IPR-1804 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Junction | SSFL, Up Main, Down Main | 2025-05-02 22:30 | 2025-05-05 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. | Neil Doust | Warren Williams |  | LPA | 2023-11-10
IPR-1805 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Junction | Cootamundra | All Lines | 2025-05-03 06:00 | 2025-05-04 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Goulburn;#Goulburn to Junee | Extended Config 14 Possession Moss Vale (Inclusive) to Cootamundra (Exclusive). Access Open to Cootamundra West from Cootamundra Yard | Neil Doust | Warren Williams |  | LPA | 2023-11-10
IPR-2502 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Taree | Grafton City | All Lines | 2025-05-17 05:00 | 2025-05-18 19:30 | 38:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Taree (Inclusive) to Grafton City (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2866 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2025-05-17 05:00 | 2025-05-17 15:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 46- Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2501 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Grafton City | Casino | All Lines | 2025-05-17 05:30 | 2025-05-18 17:00 | 35:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Grafton City (Inclusive) to Casino (Inclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2868 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2025-05-17 05:30 | 2025-05-17 15:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1800 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Taree | All Lines | 2025-05-17 07:00 | 2025-05-19 01:00 | 42:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Telarah to Taree (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2498 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Casino | Acacia Ridge | All Lines | 2025-05-17 07:00 | 2025-05-18 18:00 | 35:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Casino (Exclusive) to Acacia Ridge (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2867 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2025-06-07 05:00 | 2025-06-07 15:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 49- Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2869 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2025-06-07 05:30 | 2025-06-07 15:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1793 | 2023-11-24 | Supported |  |  | 1 | Config 10-A | Port Botany Yard | Flemington Goods Jct | All Lines | 2025-06-28 02:00 | 2025-06-30 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 A Possession. Flemington Goods Closed, Sefton Junction Open into SOY. SSFL Open | Neil Doust | Warren Williams |  | LPA | 2023-11-15

## NSW & QLD Possessions
Request_ID | Customer Advised | Possessions Status | TAA # | Date Published | Operator Impact | Possession Type | Location From | Location To | Track | Start Time | Finish Time | Total Duration(hr) | Scope of Work | Corridor | Line Segments Affected | Comments for Customers | Assigned | Contact Person for the Request | Safe Working Limits (From) | Safeworking Requirements | Date Submitted
IPR-2960 | 2024-06-19 | Approved | 0927-2024 | 2024-06-20 | 3 | Urgent Possession | Enfield West | Leightonfield | SSFL | 2024-06-24 12:30 | 2024-06-24 23:00 | 10:30 | Sefton Dive Pump | North - South | Southern Sydney Freight Line | Windows for ad hocs will be 1630-1800hrs and 1900-2030hrs. Mandatories as planned. | Andrew Duncan | Jensen Kelly | EW418 Signal to LF4 and LF6 Signals |  | 2024-06-18
IPR-2723 | 2024-05-16 | Approved | 0731-2024 | 2024-05-17 | 3 | Total Possession | Harden | Yass Jct | Up and Down Main | 2024-06-24 13:00 | 2024-06-24 16:30 | 3:30 | Resurfacing | North - South | Goulburn to Junee | 0700-0800, Up Main, Harden to Galong. 0800-1000, Up Main, Galong to Yass Junction. 1200-1500, Down Main, Yass Junction to Harden | Andrew Duncan | Curtis McClelland |  |  | 2024-04-23
IPR-2898 | 2024-04-30 | Approved | 0001-2024 | 2024-04-30 | 1 | Total Possession | Glenfield | Leightonfield | SSFL | 2024-06-24 13:00 | 2024-06-24 17:00 | 4:00 | Cabramatta Loop Project Construction Work | North - South | Southern Sydney Freight Line | ​4.5hr Total Possession Window. Possession occurs in a Natural 'No-Train' Period. Unhealthy trains will be delayed. Train Alterations will be on TAA 0531-2024 | Andrew Duncan | Miguel Alcantara | LF13, LF11 to GF22, 18, 16. | LPA | 2024-04-24
IPR-2324-1786 | 2023-08-24 | Approved | 0019-2024 | 2023-12-08 | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-06-24 16:00 | 2024-06-24 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | John Hilton | Sheree Chellas |  |  | 2023-08-21
IPR-2797 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-25 08:00 | 2024-06-25 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2724 | 2024-05-16 | Approved | 0731-2024 | 2024-05-17 | 3 | Total Possession | Yass Jct | Harden | Up and Down Main | 2024-06-25 08:30 | 2024-06-25 15:30 | 7:00 | Resurfacing | North - South | Goulburn to Junee | 0830-1100, Down Main, Yass Junction to Harden. 1300-1530, Yass Junction, Up Main within Yard Limits. | Andrew Duncan | Curtis McClelland |  |  | 2024-04-23
IPR-2798 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-26 08:00 | 2024-06-26 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2725 | 2024-05-16 | Approved | 0732-2024 | 2024-05-17 | 3 | Total Possession | Moss Vale | Dombarton | Single Main | 2024-06-27 07:00 | 2024-06-27 12:00 | 5:00 | Resurfacing | North - South | Macarthur to Moss Vale | Resurfacing on Single Main. No trains through window. | Andrew Duncan | Curtis McClelland |  |  | 2024-04-23
IPR-2799 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-27 08:00 | 2024-06-27 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2726 | 2024-05-16 | Approved | 0732-2024 | 2024-05-17 | 3 | Total Possession | Moss Vale | Dombarton | Single Main | 2024-06-28 08:00 | 2024-06-28 18:30 | 10:30 | Resurfacing | North - South | Macarthur to Moss Vale | Resurfacing between Mandatory trains. 0800-1130 then 1530-1830. | Andrew Duncan | Curtis McClelland |  |  | 2024-04-23
IPR-2800 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-28 08:00 | 2024-06-28 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2901 | 2024-05-23 | Approved | 0816-2024 | 2024-05-27 | 3 | Window Possession | Goulburn | Lynwood | Up Main | 2024-06-28 10:00 | 2024-06-28 17:00 | 7:00 | Ultrasonic Testing | North - South | Moss Vale to Goulburn | Critical compliance testing, Adhos with approval,MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2079 | 2023-11-30 | Approved | 0689-2024 | 2024-06-14 | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-06-29 06:00 | 2024-06-29 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 53 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2922 | 2024-06-14 | Approved | 0898-2024 | 2024-06-14 | 1 | Total Possession | Cootamundra | Cootamundra | All | 2024-06-29 06:00 | 2024-06-29 12:30 | 6:30 | URGENT Gundagai Rd L/Xing software upgrades | North - South | Goulburn to Junee | NO AD HOCS | Neil Doust | Akhil Chopra |  |  | 2024-06-14
IPR-2089 | 2023-11-30 | Approved | 0689-2024 | 2024-06-14 | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-06-29 06:30 | 2024-06-29 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-2801 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-29 08:00 | 2024-06-29 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2802 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-30 08:00 | 2024-06-30 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2902 | 2024-05-23 | Approved | 0816-2024 | 2024-05-27 | 3 | Window Possession | Goulburn | Lynwood | Up Main | 2024-06-30 10:00 | 2024-06-30 17:00 | 7:00 | Ultrasonic Testing | North - South | Moss Vale to Goulburn | Critical compliance testing, Adhos with approval,MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2843 | 2024-05-23 | Approved | 0909-2024 | 2024-06-20 | 3 | Window Possession | Yass Jct | Joppa Jct | Up and Down Main | 2024-07-01 04:30 | 2024-07-01 14:00 | 9:30 | Resurfacing | North - South | Goulburn to Junee | 0430-0730, 0930-1100 Up Main. Then 1100-1400 Down Main | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2961 | 2024-06-19 | Approved | 0927-2024 | 2024-06-20 | 3 | Window Possession | Enfield West | Leightonfield | SSFL | 2024-07-01 07:00 | 2024-07-01 09:00 | 2:00 | Sefton Dive Pump | North - South | Southern Sydney Freight Line | No ad hocs. Mandatories as planned. | Andrew Duncan | Jensen Kelly | EW418 Signal to LF4 and LF6 Signals |  | 2024-06-18
IPR-2803 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-01 08:00 | 2024-07-01 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2962 | 2024-06-19 | Approved | 0927-2024 | 2024-06-20 | 3 | Window Possession | Enfield West | Leightonfield | SSFL | 2024-07-01 13:00 | 2024-07-01 16:30 | 3:30 | Sefton Dive Pump | North - South | Southern Sydney Freight Line | No ad hocs. Mandatories as planned. | Andrew Duncan | Jensen Kelly | EW418 Signal to LF4 and LF6 Signals |  | 2024-06-18
IPR-2015 | 2023-08-24 | Approved | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-07-01 16:00 | 2024-07-01 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2844 | 2024-05-23 | Approved | 0909-2024 | 2024-06-20 | 3 | Window Possession | Yass Jct | Goulburn | Up and Down Main | 2024-07-02 07:30 | 2024-07-02 14:00 | 6:30 | Resurfacing | North - South | Goulburn to Junee | 0730-1000 + 1130-1400 Down Main. | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2804 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-02 08:00 | 2024-07-02 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2805 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-03 08:00 | 2024-07-03 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2845 | 2024-05-23 | Approved | 0909-2024 | 2024-06-20 | 3 | Window Possession | Goulburn | Lynwood | Up and Down Main | 2024-07-03 08:30 | 2024-07-03 17:00 | 8:30 | Resurfacing | North - South | Moss Vale to Goulburn | 0830-1000 + 1500-1700 Up Main. Then 1030-1230 + 1315-1415 Down Main. | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2806 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-04 08:00 | 2024-07-04 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2925 | 2023-08-24 | Approved | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-07-08 16:00 | 2024-07-08 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2807 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-09 08:00 | 2024-07-09 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2808 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-10 08:00 | 2024-07-10 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2100 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Acacia Ridge | Tamrookum | Main Line, Loop Line | 2024-07-10 09:30 | 2024-07-10 17:00 | 7:30 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | AR1 to TM8 | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2846 | 2024-05-23 | Approved | 0910-2024 | 2024-06-20 | 3 | Window Possession | Narwonah AWB | Goobang Jct | Single Main | 2024-07-11 07:00 | 2024-07-11 19:00 | 12:00 | Resurfacing | North - South | Parkes to Narromine Line | Timjelly - Peak Hill | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2809 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-11 08:00 | 2024-07-11 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2101 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Greenbank | Loadstone | Main Line, Loop Line | 2024-07-11 08:30 | 2024-07-11 16:00 | 7:30 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | GK1 to LE5 and LE7 | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2847 | 2024-05-23 | Approved | 0910-2024 | 2024-06-20 | 3 | Window Possession | Narwonah AWB | Goobang Jct | Single Main | 2024-07-12 07:00 | 2024-07-12 19:00 | 12:00 | Resurfacing | North - South | Parkes to Narromine Line | Peak Hill - Goobang Junction | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2810 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-12 08:00 | 2024-07-12 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2102 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Glenapp | Nammoona | Main Line, Loop Line | 2024-07-12 11:00 | 2024-07-12 18:00 | 7:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | GP8 to 104 | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-1790 | 2023-11-24 | Supported | 0820-2024 |  | 1 | Config 10-B | Port Botany Yard | Chullora Jct | All Lines | 2024-07-13 02:00 | 2024-07-15 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 B Possession (WE02) Chullora Junction North Fork Open, Flemington Goods Open, Sefton Junction Closed. SSFL Open | Shannon James | Warren Williams |  | LPA | 2023-11-15
IPR-2848 | 2024-05-23 | Approved | 0910-2024 | 2024-06-20 | 3 | Window Possession | Bogan Gate | Goobang Jct | Single Main | 2024-07-13 07:00 | 2024-07-13 19:00 | 12:00 | Resurfacing | North - South | Goobang Junction to Broken Hill |  | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2811 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-13 08:00 | 2024-07-13 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2103 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Kyogle | Grafton | Main Line, Loop Line | 2024-07-13 10:00 | 2024-07-13 16:00 | 6:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | KE1 to 45-4 | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2104 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Lawrence Road | Glenreagh | Main Line, Loop Line | 2024-07-14 06:30 | 2024-07-14 14:30 | 8:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 47 11M and 47 11L to 41-4 | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2849 | 2024-05-23 | Approved | 0911-2024 | 2024-06-20 | 3 | Window Possession | Cootamundra West | Goobang Jct | Single Main | 2024-07-14 07:00 | 2024-07-14 19:00 | 12:00 | Resurfacing | North - South | Cootamundra West to Goobang Junction | Working Parkes - Cootamundra West | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2812 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-14 08:00 | 2024-07-14 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2105 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Grafton | Boambee Beach | Main Line, Loop Line | 2024-07-15 07:00 | 2024-07-15 15:00 | 8:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 45-4 to 37-3 | TOA | 2023-12-06
IPR-2850 | 2024-05-23 | Approved | 0911-2024 | 2024-06-20 | 3 | Window Possession | Cootamundra West | Goobang Jct | Single Main | 2024-07-15 07:00 | 2024-07-15 19:00 | 12:00 | Resurfacing | North - South | Cootamundra West to Goobang Junction | Working Parkes - Cootamundra West | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2813 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-15 08:00 | 2024-07-15 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2926 | 2023-08-24 | Approved | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-07-15 16:00 | 2024-07-15 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2851 | 2024-05-23 | Approved | 0911-2024 | 2024-06-20 | 3 | Window Possession | Cootamundra West | Goobang Jct | Single Main | 2024-07-16 07:00 | 2024-07-16 19:00 | 12:00 | Resurfacing | North - South | Cootamundra West to Goobang Junction | Working Parkes - Cootamundra West | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2814 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-16 08:00 | 2024-07-16 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2106 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Nana Glen | Nambucca Heads | Main Line, Loop Line | 2024-07-16 09:00 | 2024-07-16 13:30 | 4:30 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 40-4 to 34-3 | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2107 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Boambee Beach | Tamban | Main Line, Loop Line | 2024-07-17 05:30 | 2024-07-17 14:00 | 8:30 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 37-3 Signal to 31-3 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2852 | 2024-05-23 | Approved | 0911-2024 | 2024-06-20 | 3 | Window Possession | Cootamundra West | Goobang Jct | Single Main | 2024-07-17 07:00 | 2024-07-17 19:00 | 12:00 | Resurfacing | North - South | Cootamundra West to Goobang Junction | Working Parkes - Cootamundra West | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2815 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-17 08:00 | 2024-07-17 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2609 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Parkes | Condobolin | Single Main | 2024-07-18 06:00 | 2024-07-18 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2108 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Nambucca Heads | Kundabung | Main Line, Loop Line | 2024-07-18 07:45 | 2024-07-18 17:45 | 10:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 34-3 Signal to 29-4 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2816 | 2024-03-13 | Approved | 0751-2024 | 2024-05-17 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-07-18 08:00 | 2024-07-18 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2610 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Condobolin | Euabalong West | Single Main | 2024-07-19 06:00 | 2024-07-19 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2109 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Tamban | Johns River | Main Line, Loop Line | 2024-07-19 23:00 | 2024-07-20 03:00 | 4:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 31-3 Signal to 24-4 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2611 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Condobolin | Euabalong West | Single Main | 2024-07-20 06:00 | 2024-07-20 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2113 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Kerewong | Killawarra | Main Line, Loop Line | 2024-07-20 15:00 | 2024-07-20 20:00 | 5:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 26-4 Signal to 19-4 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2612 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Euabalong West | Trida | Single Main | 2024-07-21 06:00 | 2024-07-21 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2110 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Johns River | Bundook | Main Line, Loop Line | 2024-07-21 18:00 | 2024-07-22 05:00 | 11:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 24-3 Signal to 16-4 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2613 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Euabalong West | Trida | Single Main | 2024-07-22 06:00 | 2024-07-22 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2927 | 2023-08-24 | Approved | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-07-22 16:00 | 2024-07-22 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2111 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Bundook | Gloucestor | Main Line, Loop Line | 2024-07-22 19:30 | 2024-07-23 02:00 | 6:30 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities (Possible Change to Day Shift - TBC) Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 16-3 Signal to 13-2 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresse - Working from Acacia Ridge in a Up direction towards Telarah - Possible change to day shift | 2023-12-06
IPR-2614 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Trida | Ivanhoe | Single Main | 2024-07-23 06:00 | 2024-07-23 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2853 | 2024-05-23 | Approved | 0912-2024 | 2024-06-20 | 3 | Window Possession | Ettamogah | The Rock | Single Main | 2024-07-23 07:00 | 2024-07-23 19:00 | 12:00 | Resurfacing | North - South | Junee to Albury |  | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2112 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Mount George | Stroud Road | Main Line, Loop Line | 2024-07-23 20:30 | 2024-07-24 05:00 | 8:30 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 17-4 Signal to 09-4 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2615 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Trida | Ivanhoe | Single Main | 2024-07-24 06:00 | 2024-07-24 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2854 | 2024-05-23 | Approved | 0912-2024 | 2024-06-20 | 3 | Window Possession | Ettamogah | The Rock | Single Main | 2024-07-24 07:00 | 2024-07-24 19:00 | 12:00 | Resurfacing | North - South | Junee to Albury |  | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2623 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Telarah | Dungog | Main Line and Crossing Loops | 2024-07-24 18:30 | 2024-07-25 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval,MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2908 | 2024-01-24 | Approved |  |  | 2 | Total Possession | Gloucestor | Monkerai | Main Line, Loop Line | 2024-07-24 19:00 | 2024-07-25 05:00 | 10:00 | Rail Grinding | North - South | Telarah to Acacia Ridge | Rail Grinding activities. Path alterations may be required. Ad Hoc Service RestrictionsPossession limits and shift times to be modified as planning progresses Working from Acacia Ridge towards Telarah in the Up Direction | Shannon James | Alex Summerville | 13-2 Signal to 08-3 Signal | No Adhoc Possessions - limits and shift times to be modified as planning progresses - Working from Acacia Ridge in a Up direction towards Telarah | 2023-12-06
IPR-2616 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Ivanhoe | Menindee | Single Main | 2024-07-25 06:00 | 2024-07-25 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2855 | 2024-05-23 | Approved | 0912-2024 | 2024-06-20 | 3 | Window Possession | The Rock | Wagga Wagga | Single Main | 2024-07-25 07:00 | 2024-07-25 19:00 | 12:00 | Resurfacing | North - South | Junee to Albury |  | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2624 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Dungog | Craven North | Main Line and Crossing Loops | 2024-07-25 18:30 | 2024-07-26 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2617 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Ivanhoe | Menindee | Single Main | 2024-07-26 06:00 | 2024-07-26 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2856 | 2024-05-23 | Approved | 0912-2024 | 2024-06-20 | 3 | Window Possession | Uranquinty | Junee | Single Main | 2024-07-26 07:00 | 2024-07-26 19:00 | 12:00 | Resurfacing | North - South | Junee to Albury |  | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2625 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Craven North | Mount George | Main Line and Crossing Loops | 2024-07-26 18:30 | 2024-07-27 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2080 | 2023-11-30 | Approved | 0892-2024 |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-07-27 06:00 | 2024-07-27 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 04 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2618 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Ivanhoe | Menindee | Single Main | 2024-07-27 06:00 | 2024-07-27 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2090 | 2023-11-30 | Approved | 0892-2024 |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-07-27 06:30 | 2024-07-27 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-2857 | 2024-05-23 | Approved | 0912-2024 | 2024-06-20 | 3 | Window Possession | Uranquinty | Junee | Single Main | 2024-07-27 07:00 | 2024-07-27 19:00 | 12:00 | Resurfacing | North - South | Junee to Albury |  | Andrew Duncan | Tofiq Ahmed |  |  | 2024-05-23
IPR-2626 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Mount George | Taree | Main Line and Crossing Loops | 2024-07-27 18:30 | 2024-07-28 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2619 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Ivanhoe | Menindee | Single Main | 2024-07-28 06:00 | 2024-07-28 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2627 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Taree | Kendall | Main Line and Crossing Loops | 2024-07-28 18:30 | 2024-07-29 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2620 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Menindee | Broken Hill | Single Main | 2024-07-29 06:00 | 2024-07-29 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-10
IPR-2928 | 2023-08-24 | Approved | 0019-2024 |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-07-29 16:00 | 2024-07-29 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2628 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Kendall | Kundabung | Main Line and Crossing Loops | 2024-07-29 18:30 | 2024-07-30 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2621 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Menindee | Broken Hill | Single Main | 2024-07-30 06:00 | 2024-07-30 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2629 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Taree | Kundabung | Main Line and Crossing Loops | 2024-07-30 18:30 | 2024-07-31 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2622 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Menindee | Broken Hill | Single Main | 2024-07-31 06:00 | 2024-07-31 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2630 | 2024-05-23 | Approved | 0868-2024 | 2024-06-14 | 3 | Window Possession | Taree | Kundabung | Main | 2024-07-31 18:30 | 2024-08-01 04:30 | 10:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2776 | 2024-05-23 | Approved | 0890-2024 | 2024-06-14 | 3 | Window Possession | Menindee | Broken Hill | Single Main | 2024-08-01 06:00 | 2024-08-01 18:00 | 12:00 | Ultrasonic Testing | East - West | Goobang Junction to Broken Hill | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2346 | 2024-02-26 | Supported | 0790-2024 |  | 1 | Total Possession | Flemington Goods Jct | Chullora Jct | Up and Down Goods Line | 2024-08-03 02:00 | 2024-08-05 02:00 | 48:00 | Sydney Trains Track Reconditioning & Rerailing | North - South | Sydney MFN | Adjoining Sydney Trains C9 Possession - Flemington Track Reconditioning & Re-Railing Down Enfield West Fork on Sydney Trains Side of Boundary Possession Down Enfield West Fork 19.84KMs to 20.300KMs of TAA Requested for 500 meters restriction of scope | Neil Doust | Jensen Kelly | Up Goods Clear of 347 Crossover to inclusive of ED 18.8 Signal (ST & ARTC Boundary) Down Goods - Clear of Signal ED 262D to Inclusive of ST 369 SJD (ST & ARTC Boundary) Chullora Junction Up North Fork - Clear of 351 Crossover to Inclusive of 348 Crossover | LPA | 2024-02-21
IPR-1797 | 2023-11-24 | Supported | 0789-2024 |  | 1 | Config 9 | Telarah | Taree | All Lines | 2024-08-03 03:00 | 2024-08-06 | 69:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Stage 1 - Telarah to Taree (Exclusive) | Neil Doust | Warren Williams | Telarah to Taree (Clear of Yard) | LPA | 2023-11-11
IPR-2492 | 2023-11-24 | Supported | 0789-2024 |  | 1 | Config 9 | Taree | Grafton City | All Lines | 2024-08-03 05:30 | 2024-08-05 19:00 | 61:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Stage 2 - Taree (Inclusive) to Grafton City (Exclusive) | Neil Doust | Warren Williams |  | LPA | 2023-11-11
IPR-2493 | 2023-11-24 | Supported | 0789-2024 |  | 1 | Config 9 | Grafton City | Casino | All Lines | 2024-08-03 05:30 | 2024-08-05 17:00 | 59:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Stage 3 - Grafton City (Inclusive) to Casino (Inclusive) | Neil Doust | Warren Williams |  | LPA | 2023-11-11
IPR-2494 | 2023-11-24 | Supported | 0789-2024 |  | 1 | Config 9 | Casino | Acacia Ridge | All Lines | 2024-08-03 05:30 | 2024-08-05 19:00 | 61:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Stage 4 - Casino (Exclusive) to Acacia Ridge (Exclusive) | Neil Doust | Warren Williams |  | LPA | 2023-11-11
IPR-2929 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-08-05 16:00 | 2024-08-05 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2775 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Loadstone | Acacia Ridge | Main | 2024-08-06 06:00 | 2024-08-06 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2777 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Loadstone | Acacia Ridge | Main | 2024-08-07 06:00 | 2024-08-07 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2778 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Grafton | Loadstone | Main | 2024-08-08 06:00 | 2024-08-08 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2779 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Grafton | Loadstone | Main | 2024-08-09 06:00 | 2024-08-09 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2913 | 2024-03-25 | Approved | 0881-2024 | 2024-06-14 | 2 | Total Possession | Broken Hill | Broken Hill | Branch Line | 2024-08-09 06:00 | 2024-08-09 18:00 | 12:00 | Reconditioning Iodide St Lvl-X . Branch Line Track Replacement | East - West | Goobang Junction to Broken Hill | MANDATORY TRAINS AND ROAD TRAFFIC TO BE MANAGED . NO ADHOCS | Neil Doust | Bonnar Mahains
IPR-2780 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Grafton | Loadstone | Main | 2024-08-10 06:00 | 2024-08-10 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2914 | 2024-03-25 | Approved | 0881-2024 | 2024-06-14 | 2 | Total Possession | Broken Hill | Broken Hill | Main Line | 2024-08-10 06:00 | 2024-08-10 18:00 | 12:00 | Reconditioning Iodide St Lvl-X . Main Line Track Replacement | East - West | Goobang Junction to Broken Hill | MANDATORY TRAINS AND ROAD TRAFFIC TO BE MANAGED . NO ADHOCS | Neil Doust | Bonnar Mahains
IPR-2756 | 2024-05-23 | Pending |  |  | 3 | Window Possession | Junee | Jindalee | Up Main | 2024-08-10 07:00 | 2024-08-10 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Up Main. PSW via Down Main. | Andrew Duncan | Owen Blake |  |  | 2024-05-06
IPR-2781 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Lawrence Road | Grafton | Main | 2024-08-11 06:00 | 2024-08-11 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2757 | 2024-05-23 | Pending |  |  | 3 | Window Possession | Jindalee | Junee | Down Main | 2024-08-11 07:00 | 2024-08-11 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Down Main. PSW via Up Main. Alterations to mandatories. | Andrew Duncan | Owen Blake |  |  | 2024-05-06
IPR-2782 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Lawrence Road | Grafton | Main | 2024-08-12 06:00 | 2024-08-12 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2915 | 2024-03-25 | Approved | 0881-2024 | 2024-06-14 | 2 | Total Possession | Broken Hill | Broken Hill | Main & Branch Lines | 2024-08-12 06:00 | 2024-08-12 14:00 | 8:00 | Reconditioning Iodide St Lvl-X . Asphalting. | East - West | Goobang Junction to Broken Hill | MANDATORY TRAINS AND ROAD TRAFFIC TO BE MANAGED . NO ADHOCS | Neil Doust | Bonnar Mahains
IPR-2758 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Jindalee | Harden | Up Main | 2024-08-12 07:00 | 2024-08-12 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Up Main. PSW via Down Main. Alterations to mandatories. | Andrew Duncan | Owen Blake | Jindalee CA05 Signal to Harden HN28 Signal |  | 2024-05-06
IPR-2930 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-08-12 16:00 | 2024-08-12 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2759 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Harden | Jindalee | Down Main | 2024-08-13 07:00 | 2024-08-13 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Down Main. PSW via Up Main. Alterations to mandatories. | Andrew Duncan | Owen Blake | Harden Clr of 105pts to Jindalee CA03 Signal |  | 2024-05-06
IPR-2760 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Harden | Yass Jct | Up Main | 2024-08-14 07:00 | 2024-08-14 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Up Main. PSW via Down Main. Alterations to mandatories. | Andrew Duncan | Owen Blake | Harden Clr of 105pts to Yass Junction YJ24 Signal |  | 2024-05-06
IPR-2761 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Yass Jct | Galong | Down Main | 2024-08-15 07:00 | 2024-08-15 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Down Main. PSW via Up Main. Alterations to mandatories. | Andrew Duncan | Owen Blake | Yass Junction YJ18 Signal to Galong 364.9 Signal |  | 2024-05-06
IPR-2762 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Galong | Harden | Down Main | 2024-08-16 07:00 | 2024-08-16 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Down Main. PSW via Up Main. Alterations to mandatories. | Andrew Duncan | Owen Blake | Galong 364.9 Signal to Harden HN15 Signal |  | 2024-05-06
IPR-2081 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-08-17 06:00 | 2024-08-17 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 07 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2091 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-08-17 06:30 | 2024-08-17 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-2931 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-08-19 16:00 | 2024-08-19 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2783 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Glenreagh | Lawrence Road | Main | 2024-08-21 06:00 | 2024-08-21 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2784 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Glenreagh | Lawrence Road | Main | 2024-08-22 06:00 | 2024-08-22 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2785 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Boambee Beach | Glenreagh | Main | 2024-08-23 06:00 | 2024-08-23 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2786 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Boambee Beach | Glenreagh | Main | 2024-08-24 06:00 | 2024-08-24 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2789 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Albury | The Rock | Main | 2024-08-24 06:00 | 2024-08-24 18:00 | 12:00 | Ultrasonic Testing | North - South | Junee to Albury | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-05-10
IPR-2787 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Eungai | Boambee Beach | Main | 2024-08-25 06:00 | 2024-08-25 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2790 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Albury | The Rock | Main | 2024-08-25 06:00 | 2024-08-25 18:00 | 12:00 | Ultrasonic Testing | North - South | Junee to Albury | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-05-10
IPR-2788 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Eungai | Boambee Beach | Main | 2024-08-26 06:00 | 2024-08-26 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2791 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Albury | The Rock | Main | 2024-08-26 06:00 | 2024-08-26 18:00 | 12:00 | Ultrasonic Testing | North - South | Junee to Albury | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-05-10
IPR-2932 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-08-26 16:00 | 2024-08-26 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2792 | 2024-05-23 | Supported |  |  | 3 | Window Possession | The Rock | Junee | Main | 2024-08-27 06:00 | 2024-08-27 18:00 | 12:00 | Ultrasonic Testing | North - South | Junee to Albury | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-05-10
IPR-2919 | 2024-05-23 | Supported |  |  | 3 | Window Possession | Eungai | Kundabung | Main | 2024-08-27 06:00 | 2024-08-27 18:00 | 12:00 | Ultrasonic Testing | North - South | Telarah to Acacia Ridge | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-04-09
IPR-2793 | 2024-05-23 | Supported |  |  | 3 | Window Possession | The Rock | Junee | Main | 2024-08-28 06:00 | 2024-08-28 18:00 | 12:00 | Ultrasonic Testing | North - South | Junee to Albury | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-05-10
IPR-2794 | 2024-05-23 | Supported |  |  | 3 | Window Possession | The Rock | Junee | Main | 2024-08-29 06:00 | 2024-08-29 18:00 | 12:00 | Ultrasonic Testing | North - South | Junee to Albury | Critical compliance testing, Adhos with approval, MTP operate as required | Neil Doust | Owen van der Werff |  |  | 2024-05-10
IPR-2763 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Yass Jct | Joppa Jct | Up Main | 2024-08-31 07:00 | 2024-08-31 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Up Main. PSW via Down Main. Mandatories affected. | Andrew Duncan | Owen Blake | Yass Junction YJ7 Signal to Joppa Junction G4 Signal |  | 2024-05-06
IPR-2644 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Cooks River | Enfield | Down Goods | 2024-10-19 08:00 | 2024-10-19 18:00 | 10:00 | Sydney Metro Construction Activities | North - South | Sydney MFN | Possession of the Down Goods between Cooks River & Enfield. Clear of Cooks River & Enfield Yards. NO Access from the Illawarra Lines Botany to Cooks River Remains OPEN. Impacts to: 1155 (PN), 1297 (PN), 1902 (RC), 9138 (PN), 1157 (PN), 1293 (PN). | Shannon James | Steven Payne |  | LPA | 2024-04-10
IPR-2648 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-10-19 08:00 | 2024-10-19 11:30 | 3:30 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open.Impacted Services: 1152 (PN), 2192 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2652 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-10-19 15:00 | 2024-10-19 18:00 | 3:00 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 2196 (PN), 1156 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2764 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Yass Jct | Joppa Jct | Up Main | 2024-09-01 07:00 | 2024-09-01 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Up Main. PSW via Down Main. Mandatories affected. | Andrew Duncan | Owen Blake | Yass Junction YJ7 Signal to Joppa Junction G4 Signal |  | 2024-05-06
IPR-2645 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Cooks River | Enfield | Down Goods | 2024-10-20 08:00 | 2024-10-20 18:00 | 10:00 | Sydney Metro Construction Activities | North - South | Sydney MFN | Possession of the Down Goods between Cooks River & Enfield. Clear of Cooks River & Enfield Yards. NO Access from the Illawarra Lines Botany to Cooks River Remains OPEN. Impacts to: 1297 (PN), 1155 (PN), 9102 (RC), 9138 (PN), 1157 (PN), 1293 (PN) | Shannon James | Steven Payne |  | LPA | 2024-04-10
IPR-2649 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-10-20 08:00 | 2024-10-20 11:30 | 3:30 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 1152 (PN), 2192 (PN), 1907 (RC), 2196 (PN) In conjunction with Down Goods LPA Handback window from 1130 to 1500 | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2653 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-10-20 15:00 | 2024-10-20 18:00 | 3:00 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 1156 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2765 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Joppa Jct | Yass Jct | Down Main | 2024-09-02 07:00 | 2024-09-02 17:00 | 10:00 | Rail Grinding | North - South | Goulburn to Junee | Rail Grinding on Down Main. PSW via Up Main. Mandatories affected. | Andrew Duncan | Owen Blake | Goulburn Clr of 101pts to Yass Junction YJ5 Signal |  | 2024-05-06
IPR-2933 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-09-02 16:00 | 2024-09-02 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2766 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Goulburn | Lynwood | Up Main | 2024-09-03 07:00 | 2024-09-03 17:00 | 10:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Up Main. PSW via Down Main. Mandatories affected. | Andrew Duncan | Owen Blake | Goulburn G78 Signal to Lynwood LD14 Signal |  | 2024-05-06
IPR-2767 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Marulan | Goulburn | Down Main | 2024-09-04 07:00 | 2024-09-04 17:00 | 10:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Down Main. PSW via Up Main. Mandatories affected. | Andrew Duncan | Owen Blake | Marulan Clr of E Frame to Goulburn G75 Signal |  | 2024-05-06
IPR-2768 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Marulan | Wingello | Up Main | 2024-09-05 07:00 | 2024-09-05 17:00 | 10:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Up Main. PSW via Down Main. Mandatories affected. | Andrew Duncan | Owen Blake | Wingello Clr of C Frame to Marulan Clr of E Frame |  | 2024-05-06
IPR-1794 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2024-09-07 01:00 | 2024-09-08 23:00 | 46:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN | Shannon James | Warren Williams |  | LPA | 2023-11-10
IPR-2082 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-09-07 06:00 | 2024-09-07 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 10 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) In alignment with Config 16 | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2092 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-09-07 06:30 | 2024-09-07 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line In Alignment with Config 16 | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-2934 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-09-09 16:00 | 2024-09-09 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2769 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Wingello | Marulan | Down Main | 2024-09-10 07:00 | 2024-09-10 17:00 | 10:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Down Main. PSW via Up Main. Mandatories affected. | Andrew Duncan | Owen Blake | Wingello Clr of D Frame to Marulan Clr of D Frame |  | 2024-05-06
IPR-2770 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Wingello | Moss Vale | Up Main | 2024-09-11 18:00 | 2024-09-12 06:00 | 12:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Up Main. PSW via Down Main. Mandatories affected. | Andrew Duncan | Owen Blake | Wingello Clr of D Frame to Moss Vale MV88 Signal |  | 2024-05-06
IPR-1801 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Junction | SSFL, Up Main, Down Main | 2024-09-13 22:30 | 2024-09-16 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. | Neil Doust | Warren Williams |  | LPA | 2023-11-10
IPR-1807 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Moss Vale | Goulburn | All Lines | 2024-09-14 00:01 | 2024-09-16 18:00 | 65:59 | Major Maintenance, SHOO Project Construction | North - South | Moss Vale to Goulburn | ARTC South 'Super' Possession, Aligned with Config 14. | Neil Doust | Warren Williams | Moss Vale Yard (Exclusive) to Goulburn Yard (Inclusive) | LPA | 2023-11-10
IPR-2237 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Junction | Moss Vale | All Lines | 2024-09-14 00:01 | 2024-09-16 02:00 | 49:59 | Major Maintenance | North - South | Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. | Neil Doust | Warren Williams |  | LPA | 2023-11-10
IPR-1808 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Goulburn | Albury | All Lines | 2024-09-14 03:00 | 2024-09-16 18:00 | 63:00 | Major Maintenance | North - South | Goulburn to Junee;#Junee to Albury | Aligned with ARTC Config 14 | Neil Doust | Warren Williams | Goulburn Yard (Exclusive) to Albury (Inclusive) | LPA | 2023-11-10
IPR-2430 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Cootamundra West | Forbes | All Lines | 2024-09-14 06:00 | 2024-09-16 18:00 | 60:00 | Major Maintenance | North - South | Cootamundra West to Goobang Junction | Aligned with ARTC Config 14 | Neil Doust | Warren Williams | Cootamundra West (Inclusive) to Goobang Junction (Exclusive) | TOA | 2023-11-10
IPR-2656 | 2024-05-23 | Supported | 0935-2024 |  | 1 | Total Possession | Forbes | Goobang Jct | Main Line | 2024-09-14 06:00 | 2024-09-18 10:00 | 100:00 | Inland Rail Construction Activities | North - South | Cootamundra West to Goobang Junction | WYNDHAM AVE BRIDGE Earthworks, piling & drainage DAROOBALGIE CROSSING LOOP Turnout Construction works | Andrew Duncan | Chris Fay | Forbes DYLB to GJ124 | LPA | 2024-04-05
IPR-2646 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Cooks River | Enfield | Down Goods | 2024-11-02 08:00 | 2024-11-02 18:00 | 10:00 | Sydney Metro Construction Activities | North - South | Sydney MFN | Possession of the Down Goods between Cooks River & Enfield. Clear of Cooks River & Enfield Yards. NO Access from the Illawarra Lines Botany to Cooks River Remains OPEN. Impacts to: 1155 (PN), 1297 (PN), 1902 (RC), 9138 (PN), 1157 (PN), 1293 (PN). | Shannon James | Steven Payne |  | LPA | 2024-04-10
IPR-2650 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-11-02 08:00 | 2024-11-02 11:30 | 3:30 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open.Impacted Services: 1152 (PN), 2192 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2654 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-11-02 15:00 | 2024-11-02 18:00 | 3:00 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 2196 (PN), 1156 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2647 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Cooks River | Enfield | Down Goods | 2024-11-03 08:00 | 2024-11-03 18:00 | 10:00 | Sydney Metro Construction Activities | North - South | Sydney MFN | Possession of the Down Goods between Cooks River & Enfield. Clear of Cooks River & Enfield Yards. NO Access from the Illawarra Lines Botany to Cooks River Remains OPEN. Impacts to: 1297 (PN), 1155 (PN), 9102 (RC), 9138 (PN), 1157 (PN), 1293 (PN) | Shannon James | Steven Payne |  | LPA | 2024-04-10
IPR-2651 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-11-03 08:00 | 2024-11-03 11:30 | 3:30 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 1152 (PN), 2192 (PN), 1907 (RC), 2196 (PN) In conjunction with Down Goods LPA Handback window from 1130 to 1500 | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2655 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-11-03 15:00 | 2024-11-03 18:00 | 3:00 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 1156 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2935 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-09-16 16:00 | 2024-09-16 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2771 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Moss Vale | Wingello | Down Main | 2024-09-17 18:00 | 2024-09-18 06:00 | 12:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Down Main. PSW via Up Main. Mandatories affected. | Andrew Duncan | Owen Blake | Moss Vale MV79 Signal to Wingello Clr of C Frame |  | 2024-05-06
IPR-2772 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Goulburn | Joppa Jct | Up Main | 2024-09-18 18:00 | 2024-09-19 06:00 | 12:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Up Main. PSW via Down Main. Mandatories affected. | Andrew Duncan | Owen Blake | Within Goulburn Yard Limits |  | 2024-05-06
IPR-2773 | 2024-05-23 | Pending |  |  | 2 | Total Possession | Joppa Jct | Goulburn | Down Main | 2024-09-19 18:00 | 2024-09-20 06:00 | 12:00 | Rail Grinding | North - South | Moss Vale to Goulburn | Rail Grinding on Down Main. PSW via Up Main. Mandatories affected. | Andrew Duncan | Owen Blake | Within Goulburn Yard Limits |  | 2024-05-06
IPR-2936 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-09-23 16:00 | 2024-09-23 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2937 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-09-30 16:00 | 2024-09-30 22:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2938 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-10-07 17:00 | 2024-10-07 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2083 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-10-12 06:00 | 2024-10-12 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 16 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2093 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-10-12 06:30 | 2024-10-12 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-2939 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-10-14 17:00 | 2024-10-14 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2940 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-10-21 17:00 | 2024-10-21 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2941 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-10-28 17:00 | 2024-10-28 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2495 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Taree | Grafton City | All Lines | 2024-11-02 05:00 | 2024-11-03 19:30 | 38:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Taree (Inclusive) to Grafton City (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2496 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Grafton City | Casino | All Lines | 2024-11-02 05:30 | 2024-11-03 17:00 | 35:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Grafton City (Inclusive) to Casino (Inclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2084 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-11-02 06:00 | 2024-11-02 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 18 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) In alignment with Config 9 | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2094 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-11-02 06:30 | 2024-11-02 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1798 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Taree | All Lines | 2024-11-02 07:00 | 2024-11-04 01:00 | 42:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Telarah to Taree (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2497 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Casino | Acacia Ridge | All Lines | 2024-11-02 07:00 | 2024-11-03 18:00 | 35:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Casino (Exclusive) to Acacia Ridge (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2942 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-11-04 17:00 | 2024-11-04 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2943 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-11-11 17:00 | 2024-11-11 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-2944 | 2023-08-24 | Approved |  |  | 1 | Maintenance Window | Goobang Jct | Goobang Jct | All Lines, including North West Link | 2024-11-18 17:00 | 2024-11-18 23:00 | 6:00 | Weekly Maintenance Window | North - South | Goobang Junction to Broken Hill | Weekly ​Maintenance Window.No Access to Goobang Junction or North West Link. Late Services may be impacted No Ad Hoc Services or Unplanned Shunting | Neil Doust | Steven Towns |  |  | 2023-08-21
IPR-1802 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Junction | SSFL, Up Main, Down Main | 2024-11-22 22:30 | 2024-11-25 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. | Andrew Duncan | Warren Williams |  | LPA | 2023-11-10
IPR-1806 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Junction | Cootamundra | All Lines | 2024-11-23 06:00 | 2024-11-24 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Goulburn;#Goulburn to Junee | Extended Config 14 Possession Moss Vale (Inclusive) to Cootamundra (Exclusive). Access Open to Cootamundra West from Cootamundra Yard | Andrew Duncan | Warren Williams |  | LPA | 2023-11-10
IPR-1795 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2024-11-30 01:00 | 2024-12-01 23:00 | 46:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN. (WE22) | Neil Doust | Warren Williams |  | LPA | 2023-11-10
IPR-1792 | 2023-11-24 | Supported |  |  | 1 | Config 10-A | Port Botany Yard | Flemington Goods Jct | All Lines | 2024-12-07 02:00 | 2024-12-09 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 A Possession (WE23) Flemington Goods Closed, Sefton Junction Open into SOY. SSFL Open | Shannon James | Warren Williams |  | LPA | 2023-11-15
IPR-2085 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2024-12-14 06:00 | 2024-12-14 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 24 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2095 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2024-12-14 06:30 | 2024-12-14 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-2858 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2025-01-18 06:00 | 2025-01-18 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 29 - Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2859 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2025-01-18 06:30 | 2025-01-18 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-2503 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Taree | Grafton City | All Lines | 2025-02-08 05:00 | 2025-02-09 19:30 | 38:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Taree (Inclusive) to Grafton City (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2500 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Grafton City | Casino | All Lines | 2025-02-08 05:30 | 2025-02-09 17:00 | 35:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Grafton City (Inclusive) to Casino (Inclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2860 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2025-02-08 06:00 | 2025-02-08 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 32- Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2861 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2025-02-08 06:30 | 2025-02-08 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1799 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Taree | All Lines | 2025-02-08 07:00 | 2025-02-10 01:00 | 42:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Telarah to Taree (Exclusive) | Andrew Duncan | Warren Williams |  | LPA | 2023-11-11
IPR-2499 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Casino | Acacia Ridge | All Lines | 2025-02-08 07:00 | 2025-02-09 18:00 | 35:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Casino (Exclusive) to Acacia Ridge (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2871 | 2024-05-23 | Pending |  |  | 1 | Total Possession | Condobolin | Goobang Jct | All Lines | 2025-02-22 06:00 | 2025-02-24 18:00 | 60:00 | Multiple Culvert Replacements | East - West | Goobang Junction to Broken Hill | 60hr Total Track Closure.Dates & Times may be refined | Andrew Duncan | Simon Bower |  |  | 2024-05-23
IPR-2862 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2025-03-08 06:00 | 2025-03-08 16:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 36- Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2864 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2025-03-08 06:30 | 2025-03-08 16:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1803 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Junction | SSFL, Up Main, Down Main | 2025-03-21 22:30 | 2025-03-24 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains (WE38) | Shannon James | Warren Williams |  | LPA | 2023-11-10
IPR-1810 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Moss Vale | Goulburn | All Lines | 2025-03-22 00:01 | 2025-03-24 18:00 | 65:59 | Major Maintenance, SHOO Project Construction | North - South | Moss Vale to Goulburn | ARTC South 'Super' Possession, Aligned with Config 14. | Shannon James | Warren Williams | Moss Vale Yard (Exclusive) to Goulburn Yard (Inclusive) | LPA | 2023-11-10
IPR-2238 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Junction | Moss Vale | All Lines | 2025-03-22 00:01 | 2025-03-24 02:00 | 49:59 | Major Maintenance | North - South | Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. | Neil Doust | Warren Williams |  | LPA | 2023-11-10
IPR-1809 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Goulburn | Albury | All Lines | 2025-03-22 03:00 | 2025-03-24 18:00 | 63:00 | Major Maintenance | North - South | Goulburn to Junee;#Junee to Albury | Aligned with ARTC Config 14 | Shannon James | Warren Williams | Goulburn Yard (Exclusive) to Albury (Inclusive) | LPA | 2023-11-10
IPR-2431 | 2023-11-24 | Supported |  |  | 1 | South 'Super' Possession | Cootamundra West | Goobang Jct | All Lines | 2025-03-22 06:00 | 2025-03-24 18:00 | 60:00 | Major Maintenance | North - South | Cootamundra West to Goobang Junction | Aligned with ARTC Config 14 | Neil Doust | Warren Williams | Cootamundra West (Inclusive) to Goobang Junction (Exclusive) | TOA | 2023-11-10
IPR-1791 | 2023-11-24 | Supported |  |  | 1 | Config 10-B | Port Botany Yard | Chullora Jct | All Lines | 2025-03-29 02:00 | 2025-03-31 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 B Possession.Chullora Junction North Fork Open, Flemington Goods Open, Sefton Junction Closed. SSFL Open | Neil Doust | Warren Williams |  | LPA | 2023-11-15
IPR-1796 | 2023-11-24 | Supported |  |  | 1 | Config 16 | Moss Vale | Unanderra | All Lines | 2025-04-12 01:00 | 2025-04-13 23:00 | 46:00 | Major Maintenance | North - South | Moss Vale to Unanderra | Aligned Config 16. Illawarra access via Sydney MFN | Andrew Duncan | Warren Williams |  | LPA | 2023-11-10
IPR-2863 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2025-04-12 05:00 | 2025-04-12 15:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 41- Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2865 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2025-04-12 05:30 | 2025-04-12 15:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1804 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Enfield West | Berrima Junction | SSFL, Up Main, Down Main | 2025-05-02 22:30 | 2025-05-05 02:00 | 51:30 | Major Maintenance | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Aligned Config 14 with Sydney Trains. | Neil Doust | Warren Williams |  | LPA | 2023-11-10
IPR-1805 | 2023-11-24 | Supported |  |  | 1 | Config 14 | Berrima Junction | Cootamundra | All Lines | 2025-05-03 06:00 | 2025-05-04 18:00 | 36:00 | Major Maintenance | North - South | Moss Vale to Goulburn;#Goulburn to Junee | Extended Config 14 Possession Moss Vale (Inclusive) to Cootamundra (Exclusive). Access Open to Cootamundra West from Cootamundra Yard | Neil Doust | Warren Williams |  | LPA | 2023-11-10
IPR-2502 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Taree | Grafton City | All Lines | 2025-05-17 05:00 | 2025-05-18 19:30 | 38:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Taree (Inclusive) to Grafton City (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2866 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2025-05-17 05:00 | 2025-05-17 15:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 46- Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2501 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Grafton City | Casino | All Lines | 2025-05-17 05:30 | 2025-05-18 17:00 | 35:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Grafton City (Inclusive) to Casino (Inclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2868 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2025-05-17 05:30 | 2025-05-17 15:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1800 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Telarah | Taree | All Lines | 2025-05-17 07:00 | 2025-05-19 01:00 | 42:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Telarah to Taree (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2498 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Casino | Acacia Ridge | All Lines | 2025-05-17 07:00 | 2025-05-18 18:00 | 35:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Casino (Exclusive) to Acacia Ridge (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2867 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Glenfield | Moss Vale | SSFL, Up Main, Down Main | 2025-06-07 05:00 | 2025-06-07 15:00 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Southern Sydney Freight Line;#Macarthur to Moss Vale | Weekend 49- Monthly PMP - This Stage is clear of Moss Vale Yard Moorebank Terminal Access available from Sydney (Leightonfield) End In Conjunction with Moss Vale to Goulburn stage of PMP (0630 - 1630) | Andrew Duncan | Warren Williams | Stage 1 -- GF19, GF21 - GE25, Stage 2 -- GE23, GE25 & 36.0 - BJ87 & 87.4 | LPA, Multiple Stages | 2023-11-01
IPR-2869 | 2023-11-30 | Approved |  |  | 1 | Maintenance Window | Moss Vale | Goulburn | Up Main, Down Main, Moss Vale Down Refuge, Down Loop, Inspection Road, North Fork, South Fork, Up Refuge, Arrival Road | 2025-06-07 05:30 | 2025-06-07 15:30 | 10:00 | Monthly Preventative Maintenance Possession | North - South | Moss Vale to Goulburn | Monthly PMP - In conjunction with Glenfield to Moss Vale stages (0600 - 1600) Access to Goulburn Yard NO Access to Moss Vale Yard from the Unanderra Line 6MB4 divert via Unanderra | Andrew Duncan | Warren Williams | Stage 3 -- BJ87, BJ83, 87.4 & MV21 - G81 & G78 | LPA, Multiple Stages | 2023-11-01
IPR-1793 | 2023-11-24 | Supported |  |  | 1 | Config 10-A | Port Botany Yard | Flemington Goods Jct | All Lines | 2025-06-28 02:00 | 2025-06-30 02:00 | 48:00 | Major Maintenance Activities | North - South | Port Botany to Marrickville Jct;#Sydney MFN | Config 10 A Possession. Flemington Goods Closed, Sefton Junction Open into SOY. SSFL Open | Neil Doust | Warren Williams |  | LPA | 2023-11-15

## SA & WA Possessions
Request_ID | Customer Advised | Possessions Status | TAA # | Date Published | Operator Impact | Possession Type | Location From | Location To | Track | Start Time | Finish Time | Total Duration(hr) | Scope of Work | Corridor | Line Segments Affected | Comments for Customers | Assigned | Contact Person for the Request | Safe Working Limits (From) | Safeworking Requirements | Date Submitted
IPR-2066 | 2023-12-22 | Approved | 0774-2024 | 2024-05-24 | 2 | Total Possession | Crystal Brook | Coonamia | East Bound Mainline | 2024-06-24 20:30 | 2024-06-25 10:30 | 14:00 | Level crossing upgrade Milcowie Rd 13.714km | East - West | Crystal Brook to Spencer Junction | No Train Period on the Eastbound Mainline Only | Neil Doust | Jessica Tai |  |  | 2023-12-18
IPR-1974 | 2023-11-24 | Cancelled |  |  | 2 | Total Possession | Coondambo | Kultanaby | Mainline | 2024-06-25 13:00 | 2024-06-26 01:00 | 12:00 | Culvert replacement 379.131km | East - West | Spencer Junction to Tarcoola | No Train Period - Was 30 April | Bryce Gore | Bonnar Mahains |  |  | 2023-11-23
IPR-2067 | 2023-12-22 | Approved | 0774-2024 | 2024-05-24 | 2 | Total Possession | Crystal Brook | Coonamia | East Bound Mainline | 2024-06-25 22:20 | 2024-06-26 10:00 | 11:40 | Level crossing upgrade Milcowie Rd 13.714km | East - West | Crystal Brook to Spencer Junction | No Train Period on the Eastbound Mainline Only | Neil Doust | Jessica Tai |  |  | 2023-12-18
IPR-1978 | 2023-11-24 | Approved | 0648-2024 | 2024-05-06 | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-06-25 22:30 | 2024-06-26 10:30 | 12:00 | Culvert Replacement: 28.272km & 37.871km | East - West | Broken Hill to Crystal Brook | Was 04-09 June 2024Amendment published 16/05/2024 | Neil Doust | Bonnar Mahains |  |  | 2023-11-23
IPR-1975 | 2023-11-24 | Cancelled |  |  | 2 | Total Possession | Coondambo | Kultanaby | Mainline | 2024-06-26 11:00 | 2024-06-26 15:30 | 4:30 | Culvert replacement 379.131km | East - West | Spencer Junction to Tarcoola | No Train Period - was 1st May | Bryce Gore | Bonnar Mahains |  |  | 2023-11-23
IPR-1979 | 2023-11-24 | Approved | 0648-2024 | 2024-05-06 | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-06-26 20:15 | 2024-06-27 02:00 | 5:45 | Culvert Replacement: 28.272km & 37.871km | East - West | Broken Hill to Crystal Brook | Was 04-09 June 2024Amendment published 16/05/2024 | Neil Doust | Bonnar Mahains |  |  | 2023-11-23
IPR-1980 | 2023-11-24 | Approved | 0648-2024 | 2024-05-06 | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-06-29 03:00 | 2024-06-29 15:00 | 12:00 | Culvert Replacement: 28.272km & 37.871km | East - West | Broken Hill to Crystal Brook | Was 04-09 June 2024Amendment published 16/05/2024 | Neil Doust | Bonnar Mahains |  |  | 2023-11-23
IPR-1981 | 2023-11-24 | Approved | 0648-2024 | 2024-05-06 | 2 | Total Possession | Crystal Brook | Gladstone | Mainline | 2024-06-30 03:30 | 2024-06-30 09:30 | 6:00 | Culvert Replacement: 28.272km & 37.871km | East - West | Broken Hill to Crystal Brook | Was 04-09 June 2024Amendment published 16/05/2024 | Neil Doust | Bonnar Mahains |  |  | 2023-11-23
IPR-2903 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 3 | Total Possession | Mile End | Islington | Main Line | 2024-07-08 11:30 | 2024-07-08 17:30 | 6:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | Michael Iannella | Signal 1 Mile End to Signal 30 Islington |  | 2024-05-27
IPR-1859 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 2 | Total Possession | Mile End | Islington | Main Line | 2024-07-10 20:30 | 2024-07-11 05:30 | 9:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period - Was June | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-2909 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 3 | Total Possession | Mile End | Islington | Main Line | 2024-07-11 22:00 | 2024-07-12 03:30 | 5:30 | TRJ Project | East - West | Serviceton to Islington (SA) | No Adhoc Traffic - Moved from 1st July | Bryce Gore | Michael Iannella | Signal 1 Mile End to Signal 30 Islington |  | 2024-05-27
IPR-1873 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 2 | Total Possession | Mile End | Islington | Main Line | 2024-07-12 13:00 | 2024-07-13 01:30 | 12:30 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period - Was June | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-2969 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 3 | Total Possession | Islington | Dry Creek | Main Line | 2024-07-12 16:00 | 2024-07-12 23:00 | 7:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Adhoc Traffic - All Services Operate Under Train Order Working | Bryce Gore | Michael Iannella | Signal 1 Mile End to Signal 30 Islington |  | 2024-05-27
IPR-2910 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 3 | Total Possession | Mile End | Islington | Main Line | 2024-07-13 01:30 | 2024-07-13 11:30 | 10:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Adhoc Traffic - All Services Operate Under Train Order Working | Bryce Gore | Michael Iannella | Signal 1 Mile End to Signal 30 Islington |  | 2024-05-27
IPR-1860 | 2023-11-24 | Approved | 0897-2024 | 2024-06-18 | 2 | Total Possession | Mile End | Islington | Main Line | 2024-07-13 11:30 | 2024-07-13 23:30 | 12:00 | TRJ Project | East - West | Serviceton to Islington (SA) | No Train Period - Was June | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signal 30 Islington |  | 2023-11-20
IPR-2970 | 2024-06-24 | Approved |  |  | 3 | Total Possession | Mile End | Belair | Main Line | 2024-08-07 20:30 | 2024-08-08 05:00 | 8:30 | TRJ Project | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signals 4 & 4E Belair |  | 2024-06-21
IPR-2971 | 2024-06-24 | Approved |  |  | 3 | Total Possession | Mile End | Belair | Main Line | 2024-08-14 20:30 | 2024-08-15 05:00 | 8:30 | TRJ Project | East - West | Serviceton to Islington (SA) | No Adhoc Traffic | Bryce Gore | Michael Iannella | Signal 44 Mile End to Signals 4 & 4E Belair |  | 2024-06-21
IPR-2468 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Tent Hill | McLeay | Main Line & Loops | 2024-08-20 13:30 | 2024-08-21 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2127 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Spencer Jct | Tarcoola | Main Line & Loops | 2024-08-27 13:30 | 2024-08-28 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required Reduced down from initial 36hr request | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2700 | 2024-04-23 | Pending |  |  | 1 | Total Possession | Birkenhead | Outer Harbor | All Lines | 2024-08-31 06:00 | 2024-09-01 22:00 | 40:00 | SAPN Power Supply | East - West | Outer Harbour Line | No Train Period | Bryce Gore | Darren Schulz |  |  | 2024-04-22
IPR-2124 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Coondambo | Tarcoola | Main Line & Loops | 2024-09-03 13:30 | 2024-09-04 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2125 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Wirrappa | Pimba | Main Line & Loops | 2024-09-10 13:30 | 2024-09-11 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2126 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Pimba | Burando | Main Line & Loops | 2024-09-17 13:30 | 2024-09-18 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works (Contingency Possession) Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2469 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Pimba | Burando | Main Line & Loops | 2024-09-24 13:30 | 2024-09-25 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works (Contingency Possession) Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-1874 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Mile End | Islington | Main Line | 2024-09-30 00:01 | 2024-10-02 18:30 | 66:29 | TRJ Project Commissioning | East - West | Serviceton to Islington (SA) | ​Torrens Junction Signalling Upgrade Project - IP's & Ghan to be programmed through works | Bryce Gore | Michael Iannella | Islington Signals 32 & 34 to Mile End Signals 43, 45 & 45E |  | 2023-11-21
IPR-2963 | 2024-06-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-09-30 06:00 | 2024-10-02 06:00 | 48:00 | Underbridge Replacement 165.549km | East - West | Dry Creek to Crystal Brook | As large a windows as possible aligning with East - West Shut. Minimum 14hr No Train Period with smaller follow up window | Shannon James | Kristen Xiao | Signal 24 Snowtown to Signal 3 Redhill |  | 2024-06-21
IPR-1895 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Serviceton | Mile End | All Tracks | 2024-09-30 06:30 | 2024-10-02 18:30 | 60:00 | Major Maintenance | East - West | Serviceton to Islington (SA) | ​​Major Maintenance being conducted.Timing of Stages TBC. | Bryce Gore | Bryce Gore |  |  | 2023-11-21
IPR-2121 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Spencer Jct | Tent Hill | Main Line & Loops | 2024-10-01 13:30 | 2024-10-02 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2122 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Spencer Jct | Tent Hill | Main Line & Loops | 2024-10-08 15:00 | 2024-10-09 04:00 | 13:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2123 | 2024-01-24 | Pending |  |  | 1 | Total Possession | Tent Hill | McLeay | Main Line & Loops | 2024-10-15 13:30 | 2024-10-16 03:30 | 14:00 | Culvert Replacement | East - West | Spencer Junction to Tarcoola | Resilience Upgrade Works Dates & Times to be refined Train Cancellations & Paths Amendments Required | Bryce Gore | William Miholos |  |  | 2023-11-17
IPR-2964 | 2024-06-24 | Pending |  |  | 2 | Total Possession | Snowtown | Snowtown | Mainline & Loop | 2024-11-02 21:00 | 2024-11-03 11:00 | 14:00 | Underbridge Replacement 144km | East - West | Dry Creek to Crystal Brook | No Train Period | Shannon James | Kristen Xiao | Signals 3 to 24 Snowtown |  | 2024-06-21
IPR-2965 | 2024-06-24 | Pending |  |  | 3 | Total Possession | Snowtown | Snowtown | Mainline & Loop | 2024-11-03 22:00 | 2024-11-04 09:30 | 11:30 | Underbridge Replacement 144km | East - West | Dry Creek to Crystal Brook | No Train Period | Shannon James | Kristen Xiao | Signals 3 to 24 Snowtown |  | 2024-06-21
IPR-2966 | 2024-06-24 | Pending |  |  | 2 | Total Possession | Snowtown | Redhill | Mainline | 2024-11-09 21:00 | 2024-11-10 11:00 | 14:00 | Underbridge Replacement 148.738km | East - West | Dry Creek to Crystal Brook | No Train Period | Shannon James | Kristen Xiao | Signal 24 Snowtown to Signal 3 Redhill |  | 2024-06-21
IPR-2967 | 2024-06-24 | Pending |  |  | 3 | Total Possession | Snowtown | Redhill | Mainline | 2024-11-10 22:00 | 2024-11-11 09:30 | 11:30 | Underbridge Replacement 148.738km | East - West | Dry Creek to Crystal Brook | No Train Period | Shannon James | Kristen Xiao | Signal 24 Snowtown to Signal 3 Redhill |  | 2024-06-21
IPR-2870 | 2024-05-23 | Pending |  |  | 1 | Total Possession | Bolivar | Crystal Brook | Main | 2025-04-23 18:00 | 2025-04-26 06:00 | 60:00 | Light River Bridge Replacement | East - West | Dry Creek to Crystal Brook | Bridge Replacement - 60hr Track Closure | Bryce Gore | Kristen Xiao |  |  | 2024-05-23
IPR-2968 | 2024-06-24 | Pending |  |  | 1 | Total Possession | Snowtown | Redhill | Mainline | 2025-04-23 18:00 | 2025-04-26 06:00 | 60:00 | Underbridge Replacement 149.945 | East - West | Dry Creek to Crystal Brook | Aligns with Light River Bridge Replacement - 60hr Track Closure | Shannon James | Kristen Xiao | Signal 24 Snowtown to Signal 3 Redhill |  | 2024-06-21

## VIC Possessions
Request_ID | Customer Advised | Possessions Status | TAA # | Date Published | Operator Impact | Possession Type | Location From | Location To | Track | Start Time | Finish Time | Total Duration(hr) | Scope of Work | Corridor | Line Segments Affected | Comments for Customers | Assigned | Contact Person for the Request | Safe Working Limits (From) | Safeworking Requirements | Date Submitted
IPR-2669 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-06-24 09:00 | 2024-06-24 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2328 | 2024-02-26 | Approved | 0880-2024 | 2024-06-07 | 2 | Total Possession | Murtoa Loop | Marmalake | Main Line | 2024-06-25 06:00 | 2024-06-25 18:00 | 12:00 | 27D Pts VX Upgrade 298.365km | East - West | Tottenham to Serviceton | ​​No Train Period | Bryce Gore | Omid Hosseini |  |  | 2024-02-20
IPR-2407 | 2024-03-25 | Approved | 0735-2024 | 2024-05-24 | 3 | Window Possession | Seymour | Benalla | East / West Track | 2024-06-25 06:00 | 2024-06-25 18:00 | 12:00 | Ultrasonic Testing | North - South | Albury to Somerton | Critical compliance testing. No ad hoc services. Specific Locations/times TBC. | Neil Doust | David Knee
IPR-2603 | 2024-04-23 | Approved | 0749-2024 | 2024-05-10 | 2 | Total Possession | Benalla | Oaklands | Branch Line | 2024-06-25 06:00 | 2024-06-25 18:00 | 12:00 | Level Crossing Upgrades | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2024-04-08
IPR-2670 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-06-25 09:00 | 2024-06-25 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2408 | 2024-03-25 | Approved | 0735-2024 | 2024-05-24 | 3 | Window Possession | Benalla | Wodonga | East / West Track | 2024-06-26 06:00 | 2024-06-26 18:00 | 12:00 | Ultrasonic Testing | North - South | Albury to Somerton | Critical compliance testing. No ad hoc services. Specific Locations/times TBC. | Neil Doust | David Knee
IPR-2975 | 2024-04-23 | Approved | 0749-2024 | 2024-05-10 | 2 | Total Possession | Benalla | Oaklands | Branch Line | 2024-06-26 06:00 | 2024-06-26 18:00 | 12:00 | Level Crossing Upgrades | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2024-04-08
IPR-2671 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-06-26 09:00 | 2024-06-26 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2409 | 2024-03-25 | Approved | 0735-2024 | 2024-05-24 | 3 | Window Possession | Benalla | Wodonga | East / West Track | 2024-06-27 06:00 | 2024-06-27 18:00 | 12:00 | Ultrasonic Testing | North - South | Albury to Somerton | Critical compliance testing. No ad hoc services. Specific Locations/times TBC. | Neil Doust | David Knee
IPR-2976 | 2024-04-23 | Approved | 0749-2024 | 2024-05-10 | 2 | Total Possession | Benalla | Oaklands | Branch Line | 2024-06-27 06:00 | 2024-06-27 18:00 | 12:00 | Level Crossing Upgrades | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2024-04-08
IPR-2672 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-06-27 09:00 | 2024-06-27 17:00 | 8:00 | Inland Rail - Seymour Avenal | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2410 | 2024-03-25 | Approved | 0735-2024 | 2024-05-24 | 3 | Window Possession | Benalla | Oaklands | Single Main | 2024-06-28 06:00 | 2024-06-28 12:00 | 6:00 | Ultrasonic Testing | North - South | Benalla to Oakland Line | Critical compliance testing. No ad hoc services. Specific Locations/times TBC. | Neil Doust | David Knee
IPR-2673 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-06-28 09:00 | 2024-06-28 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2411 | 2024-03-25 | Approved | 0735-2024 | 2024-05-24 | 3 | Window Possession | Benalla | Oaklands | Single Main | 2024-06-29 06:00 | 2024-06-29 18:00 | 12:00 | Ultrasonic Testing | North - South | Benalla to Oakland Line | Critical compliance testing. No ad hoc services. Specific Locations/times TBC. | Neil Doust | David Knee
IPR-2825 | 2024-05-17 | Approved | 0786-2024 | 2024-06-04 | 2 | Total Possession | Tottenham | Tottenham | Brooklyn Leg of Tottenham Triangle | 2024-06-29 21:00 | 2024-06-30 16:00 | 19:00 | Tottenham Triangle Mixed Gauge Diamong Upgrade | East - West | Melbourne Metro | No Main or Broad Gauge services on Brooklyn Leg of Triangle | Bryce Gore | Ryan Sliwinski |  |  | 2024-05-01
IPR-2918 | 2024-02-26 | Approved | 0837-2024 | 2024-06-07 | 2 | Total Possession | Newport | Tottenham | All Lines | 2024-06-29 21:00 | 2024-06-30 09:00 | 12:00 | Sommerville Rd Brooklyn Boom | East - West | Tottenham to Serviceton | ​​No Train Period | Bryce Gore | Omid Hosseini |  |  | 2024-02-20
IPR-2324-80 | 2022-12-21 | Cancelled |  |  | 1F | Total Possession | Albion Jct | Jacana | Main Line B/G&S/G | 2024-06-29 22:00 | 2024-06-30 06:00 | 8:00 | RCP Under track Crossing | East - West | Albion to Jacana Broad Gauge;#Somerton to Tottenham Jct | ​Will coincide with normal maintenance shutdown Sunday 00:05-06:00 | Ralph Artho | Simonetta Guastella | 17.8 km-20.75 km |  | 2022-09-07
IPR-2920 | 2024-06-08 | Approved | 0878-2024 | 2024-06-07 | 2 | Total Possession | Sims St Jct | West Footscray | All Lines | 2024-06-29 22:30 | 2024-06-30 07:00 | 8:30 | Tamping & rail Scrubbing | East - West | Melbourne Metro | ​​No Train Period - No Access to Tottenham Yard | Bryce Gore | Stephen Maguire |  |  | 2024-02-20
IPR-2324-441 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-06-30 00:05 | 2024-06-30 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2412 | 2024-03-25 | Approved | 0735-2024 | 2024-05-24 | 3 | Window Possession | Wodonga | Benalla | East / West Track | 2024-06-30 06:00 | 2024-06-30 18:00 | 12:00 | Ultrasonic Testing | North - South | Albury to Somerton | Critical compliance testing. No ad hoc services. Specific Locations/times TBC. | Neil Doust | David Knee
IPR-2674 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-01 09:00 | 2024-07-01 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2675 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-02 09:00 | 2024-07-02 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2676 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-03 09:00 | 2024-07-03 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2677 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-04 09:00 | 2024-07-04 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2678 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-05 09:00 | 2024-07-05 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2826 | 2024-05-17 | Approved | 0786-2024 | 2024-06-04 | 2 | Total Possession | Tottenham | Tottenham | Brooklyn Leg of Tottenham Triangle | 2024-07-06 21:00 | 2024-07-07 08:00 | 11:00 | Tottenham Triangle Mixed Gauge Diamong Upgrade | East - West | Melbourne Metro | No Main or Broad Gauge services on Brooklyn Leg of Triangle | Bryce Gore | Ryan Sliwinski |  |  | 2024-05-01
IPR-2827 | 2024-05-17 | Approved | 0786-2024 | 2024-06-04 | 2 | Total Possession | Tottenham | Tottenham | Up & Down Broad Gauge Indepenant Goods Lines | 2024-07-06 21:00 | 2024-07-07 10:00 | 13:00 | Tottenham Triangle Mixed Gauge Diamong Upgrade | East - West | Melbourne Metro | No Broad Gauge services through to Sunshine/Albion-Jacana | Bryce Gore | Ryan Sliwinski |  |  | 2024-05-01
IPR-1985 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-07-07 00:05 | 2024-07-07 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2828 | 2024-05-17 | Approved | 0786-2024 | 2024-06-04 | 2 | Total Possession | Tottenham | Tottenham | Brooklyn Leg and Up & Down Independant Goods Legs of Tottenham Triangle | 2024-07-07 12:00 | 2024-07-07 16:00 | 4:00 | Tottenham Triangle Mixed Gauge Diamong Upgrade | East - West | Melbourne Metro | No Main or Broad Gauge services | Bryce Gore | Ryan Sliwinski |  |  | 2024-05-01
IPR-2737 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-08 09:00 | 2024-07-08 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2741 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-09 09:00 | 2024-07-09 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2742 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-10 09:00 | 2024-07-10 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2743 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-11 09:00 | 2024-07-11 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2744 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-12 09:00 | 2024-07-12 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1986 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-07-14 00:05 | 2024-07-14 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2574 | 2023-11-24 | Cancelled |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-07-15 03:00 | 2024-07-15 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2024-03-21
IPR-2713 | 2023-11-24 | Cancelled |  |  | 1 | Total Possession | Benalla | Somerton | All Standard Gauge Tracks | 2024-07-15 05:00 | 2024-07-15 19:00 | 14:00 | Inland Rail & Other Major Works | North - South | Albury to Somerton | ​14 hour Occupation | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-2911 | 2024-06-24 | Approved | 0895-2024 | 2024-06-12 | 2 | Total Possession | Benalla | Chiltern | West Track | 2024-07-15 06:00 | 2024-07-15 16:00 | 10:00 | Turnout | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Peter Morgan |  |  | 2024-06-05
IPR-2745 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-15 09:00 | 2024-07-15 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2747 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-16 09:00 | 2024-07-16 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2748 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-17 09:00 | 2024-07-17 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2749 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-18 09:00 | 2024-07-18 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | ​Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2750 | 2022-12-21 | Approved | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-19 09:00 | 2024-07-19 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd | North - South | Albury to Somerton | Single Line Running | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1987 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-07-21 00:05 | 2024-07-21 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2746 | 2022-12-21 | Cancelled | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | East Track | 2024-07-22 09:00 | 2024-07-22 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2751 | 2022-12-21 | Cancelled | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | East Track | 2024-07-23 09:00 | 2024-07-23 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2752 | 2022-12-21 | Cancelled | 0717-2024 | 2024-05-02 | 2 | Total Possession | Longwood | Seymour | East Track | 2024-07-24 09:00 | 2024-07-24 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1988 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-07-28 00:05 | 2024-07-28 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2872 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-29 09:00 | 2024-07-29 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2873 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-30 09:00 | 2024-07-30 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2874 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-07-31 09:00 | 2024-07-31 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2875 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-08-01 09:00 | 2024-08-01 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2876 | 2022-12-21 | Cancelled |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-08-02 09:00 | 2024-08-02 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1989 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-08-04 00:05 | 2024-08-04 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1990 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-08-11 00:05 | 2024-08-11 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2689 | 2024-04-23 | Pending |  |  | 2 | Total Possession | Berrybank Loop | Tooli Loop | Mainline | 2024-08-14 06:00 | 2024-08-14 18:00 | 12:00 | Re-Railing | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Derek Rowan |  |  | 2024-04-15
IPR-2690 | 2024-04-23 | Pending |  |  | 2 | Total Possession | Berrybank Loop | Tooli Loop | Mainline | 2024-08-15 06:00 | 2024-08-15 18:00 | 12:00 | Re-Railing | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Derek Rowan |  |  | 2024-04-15
IPR-1991 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-08-18 00:05 | 2024-08-18 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1992 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-08-25 00:05 | 2024-08-25 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1993 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-09-01 00:05 | 2024-09-01 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1994 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-09-08 00:05 | 2024-09-08 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1811 | 2023-11-24 | Approved |  |  | 1 | North-East Vic 'Super' Possession | Albury | Somerton | All Lines | 2024-09-14 06:00 | 2024-09-16 18:00 | 60:00 | Major Maintenance | North - South | Albury to Somerton | Aligned with ARTC Config 14 & South 'Super' Shut | Neil Doust | Warren Williams | Albury (Exclusive) to Somerton (Inclusive) | AO | 2023-11-10
IPR-1813 | 2023-11-24 | Approved |  |  | 1 | North-East Vic 'Super' Possession | Somerton | Tottenham | All ARTC Lines, Including DG & BG Lines | 2024-09-14 06:00 | 2024-09-16 18:00 | 60:00 | Major Maintenance | East - West | Somerton to Tottenham Jct;#Albion to Jacana Broad Gauge | Aligned with ARTC Config 14 & South 'Super' Shut | Neil Doust | Warren Williams | Somerton (Exclusive) to Tottenham (Exclusive) | AO | 2023-11-10
IPR-1995 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-09-15 00:05 | 2024-09-15 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1996 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-09-22 00:05 | 2024-09-22 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1997 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-09-29 00:05 | 2024-09-29 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1894 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Manor Loop | Serviceton | All Tracks | 2024-09-30 06:30 | 2024-10-02 18:30 | 60:00 | Major Maintenance | East - West | Tottenham to Serviceton | ​​Major Maintenance being conducted. Timing of Stages TBC. | Bryce Gore | Bryce Gore |  |  | 2023-11-21
IPR-1998 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-10-06 00:05 | 2024-10-06 07:00 | 6:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2900 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Wallan | Wallan | Mainline | 2024-10-07 06:00 | 2024-10-11 18:00 | 108:00 | Inland Rail Track Slew | North - South | Albury to Somerton | All Services Operate Via Crossing Loop | Bryce Gore | Tanishq Sarkar |  |  | 2024-05-27
IPR-2877 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-07 09:00 | 2024-10-07 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2878 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-08 09:00 | 2024-10-08 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2879 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-09 09:00 | 2024-10-09 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2880 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-10 09:00 | 2024-10-10 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2881 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-11 09:00 | 2024-10-11 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-1999 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-10-13 00:05 | 2024-10-13 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2882 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-14 09:00 | 2024-10-14 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2883 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-15 09:00 | 2024-10-15 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2884 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-16 09:00 | 2024-10-16 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2885 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-17 09:00 | 2024-10-17 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2886 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-18 09:00 | 2024-10-18 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2000 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-10-20 00:05 | 2024-10-20 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-1973 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-10-21 03:00 | 2024-10-21 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track - was 9th September | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-2912 | 2024-06-24 | Pending |  |  | 1 | Total Possession | Seymour | Longwood | All Tracks | 2024-10-21 06:00 | 2024-10-21 18:00 | 12:00 | Inland Rail - Seymour - Major Works | North - South | Albury to Somerton | ​12 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2024-06-06
IPR-2887 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-21 09:00 | 2024-10-21 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2888 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-22 09:00 | 2024-10-22 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2889 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-23 09:00 | 2024-10-23 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2890 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-24 09:00 | 2024-10-24 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2891 | 2022-12-21 | Approved |  |  | 2 | Total Possession | Longwood | Seymour | West Track | 2024-10-25 09:00 | 2024-10-25 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Abutment Works | North - South | Albury to Somerton | ​​SLR on East Track between 0900 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2001 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-10-27 00:05 | 2024-10-27 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2921 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Benalla | All Tracks | 2024-10-28 03:00 | 2024-10-28 21:00 | 18:00 | Glenrowan Bridge Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-2002 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-11-03 00:05 | 2024-11-03 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2003 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-11-10 00:05 | 2024-11-10 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2004 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-11-17 00:05 | 2024-11-17 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2005 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-11-24 00:05 | 2024-11-24 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2924 | 2024-06-24 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | All Lines | 2024-11-30 23:00 | 2024-12-01 08:00 | 9:00 | SCU Project | North - South | Albury to Somerton | No Train Period | Bryce Gore | Thiago Cavalcanti |  |  | 2024-06-05
IPR-2006 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-12-01 00:05 | 2024-12-01 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2007 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-12-08 00:05 | 2024-12-08 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2008 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-12-15 00:05 | 2024-12-15 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2009 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-12-22 00:05 | 2024-12-22 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2010 | 2022-12-21 | Approved | 0061-2024 | 2023-12-01 | 1 | Maintenance Window | Moonee Ponds Jct | Tullamarine | Local Line and Main Line | 2024-12-29 00:05 | 2024-12-29 06:00 | 5:55 | General Maintenance | East - West | Melbourne Metro | Weekly Maintenance Window | Bryce Gore | Raul Agoho |  |  | 2022-12-01
IPR-2829 | 2022-12-21 | Pending |  | 2024-05-02 | 2 | Total Possession | Benalla | Violet Town | West Track | 2025-03-03 06:00 | 2025-03-05 18:00 | 60:00 | Bridge Deck Renewals at 5 Sites | North - South | Albury to Somerton | ​​SLR on East Track | Bryce Gore | William Miholos |  |  | 2024-05-17
IPR-2841 | 2022-12-21 | Pending |  | 2024-05-02 | 2 | Total Possession | Benalla | Violet Town | West Track | 2025-03-06 06:00 | 2025-03-08 18:00 | 60:00 | Bridge Deck Renewals at 5 Sites | North - South | Albury to Somerton | ​​SLR on East Track | Bryce Gore | William Miholos |  |  | 2024-05-17
IPR-1812 | 2023-11-24 | Approved |  |  | 1 | North-East Vic 'Super' Possession | Albury | Somerton | All Lines | 2025-03-22 06:00 | 2025-03-24 18:00 | 60:00 | Major Maintenance | North - South | Albury to Somerton | Aligned with ARTC Config 14 & South 'Super' Possession | Shannon James | Warren Williams | Albury (Exclusive) to Somerton (Inclusive) | AO | 2023-11-10
IPR-1814 | 2023-11-24 | Approved |  |  | 1 | North-East Vic 'Super' Possession | Somerton | Tottenham | All ARTC Lines, Including DG & BG Lines | 2025-03-22 06:00 | 2025-03-24 18:00 | 60:00 | Major Maintenance | East - West | Somerton to Tottenham Jct;#Albion to Jacana Broad Gauge | Aligned with ARTC Config 14 & South 'Super' Possession | Shannon James | Warren Williams | Somerton (Exclusive) | AO | 2023-11-10

## New Requests (Last 30 Days)
Request_ID | Customer Advised | Possessions Status | TAA # | Date Published | Operator Impact | Possession Type | Location From | Location To | Track | Start Time | Finish Time | Total Duration(hr) | Scope of Work | Corridor | Line Segments Affected | Comments for Customers | Assigned | Contact Person for the Request | Safe Working Limits (From) | Safeworking Requirements | Date Submitted
IPR-2532 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-04-30 08:00 | 2024-04-30 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2533 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-01 08:00 | 2024-05-01 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2534 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-02 08:00 | 2024-05-02 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2535 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-03 08:00 | 2024-05-03 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2681 | 2024-04-19 | Approved | 0651-2024 | 2024-04-19 | 3 | Window Possession | Port Botany Yard | Cooks River | Up Botany and Cooks River Loop | 2024-05-03 21:00 | 2024-05-04 02:00 | 5:00 | Botany Rail Duplication Project | North - South | Port Botany to Marrickville Jct | Bi-Di running on Down Botany | Andrew Duncan | Samuel Hood | CR736G Signal to BY4 Signal |  | 2024-04-18
IPR-2536 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-04 08:00 | 2024-05-04 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2512 | 2023-09-25 | Approved | 0606-2024 | 2024-04-12 | 2 | Total Possession | Dry Creek | Dry Creek | Loop Line | 2024-05-04 16:00 | 2024-05-05 04:00 | 12:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Loop. Mandatory Trains to use Main line.No Adhoc Traffic No Access to MPC | Bryce Gore | Jessica Tai | Dry Creek 21 Pts (12.590km) to Dry Creek 28 Pts (13.900km) | No Train Period | 2023-09-21
IPR-2641 | 2024-04-15 | Approved | 0616-2024 | 2024-04-18 | 2 | Total Possession | Tottenham | Tottenham | All Lines | 2024-05-04 23:30 | 2024-05-05 06:00 | 6:30 | 31D points commissioning | East - West | Melbourne Metro | No Train Period | Bryce Gore | Thiago Cavalcanti |  |  | 2024-04-08
IPR-2537 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-05 08:00 | 2024-05-05 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2513 | 2023-09-25 | Approved | 0606-2024 | 2024-04-12 | 2 | Total Possession | Dry Creek | Dry Creek | Mainline and Loop | 2024-05-05 14:00 | 2024-05-05 20:00 | 6:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | No Train Period | Bryce Gore | Jessica Tai | Dry Creek 21 Pts (12.590km) to Dry Creek 28 Pts (13.900km) | No Train Period | 2023-09-21
IPR-2682 | 2024-04-19 | Approved | 0656-2024 | 2024-04-19 | 2 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-05-05 14:00 | 2024-05-05 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | No Train Period | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2024-02-21
IPR-2514 | 2023-09-25 | Approved | 0606-2024 | 2024-04-12 | 2 | Total Possession | Dry Creek | Dry Creek | Mainline | 2024-05-05 20:00 | 2024-05-06 00:30 | 4:30 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Mainline. Mandatory Trains to use Loop line when Loop is not under PossessionNo Adhoc Traffic No Access to MPC | Bryce Gore | Jessica Tai | Dry Creek 23 Pts (12.867km) to Dry Creek 25 Pts (13.797km) | No Train Period | 2023-09-21
IPR-2516 | 2023-09-25 | Approved | 0606-2024 | 2024-04-12 | 2 | Total Possession | Dry Creek | Dry Creek | Mainline and Loop | 2024-05-06 00:30 | 2024-05-06 03:30 | 3:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | No Train Period | Bryce Gore | Jessica Tai | Dry Creek 21 Pts (12.590km) to Dry Creek 28 Pts (13.900km) | No Train Period | 2023-09-21
IPR-2575 | 2023-11-24 | Approved | 0544-2024 | 2024-04-05 | 1 | Total Possession | Benalla | Somerton | Standard Gauge Lines | 2024-05-06 05:00 | 2024-05-06 18:30 | 13:30 | Inland Rail & Various Other Works | North - South | Albury to Somerton | ​No Train Period | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-2538 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-06 08:00 | 2024-05-06 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2515 | 2023-09-25 | Approved | 0606-2024 | 2024-04-12 | 2 | Total Possession | Dry Creek | Dry Creek | Main and Loop | 2024-05-06 14:00 | 2024-05-06 17:30 | 3:30 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. No Train Period Main & Loop | Bryce Gore | Jessica Tai | Dry Creek 21 Pts (12.590km) to Dry Creek 28 Pts (13.900km) | No Train Period | 2023-09-21
IPR-2607 | 2023-09-25 | Approved | 0606-2024 | 2024-04-12 | 2 | Total Possession | Dry Creek | Dry Creek | Mainline | 2024-05-06 17:30 | 2024-05-06 23:59 | 6:29 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. Full Upgrade on Mainline. Mandatory Trains to use Loop line when Loop is not under PossessionNo Adhoc Traffic No Access to MPC | Bryce Gore | Jessica Tai | Dry Creek 23 Pts (12.867km) to Dry Creek 25 Pts (13.797km) | No Train Period | 2023-09-21
IPR-2608 | 2023-09-25 | Approved | 0606-2024 | 2024-04-12 | 2 | Total Possession | Dry Creek | Dry Creek | Main and Loop | 2024-05-07 | 2024-05-07 06:00 | 6:00 | Level Crossing Upgrade | East - West | Dry Creek to Crystal Brook;#Islington (SA) to Dry Creek | Upgrade of Access Road Level Crossing. No Train Period Main & Loop | Bryce Gore | Jessica Tai | Dry Creek 21 Pts (12.590km) to Dry Creek 28 Pts (13.900km) | No Train Period | 2023-09-21
IPR-2568 | 2024-04-05 | Supported | 0550-2024 | 2024-04-23 | 1 | Total Possession | Watson | Ooldea | Main | 2024-05-07 07:00 | 2024-05-07 14:30 | 7:30 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | Unload of Ballast Train - No Train Period. Min 6hrs Continuous Required | John Hilton | Adrian Unwin |  |  | 2024-03-18
IPR-2539 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-07 08:00 | 2024-05-07 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2540 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-08 08:00 | 2024-05-08 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2541 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-09 08:00 | 2024-05-09 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2569 | 2024-04-05 | Supported | 0550-2024 | 2024-04-23 | 1 | Total Possession | Watson | Ooldea | Main | 2024-05-10 05:00 | 2024-05-10 11:00 | 6:00 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | Unload of Ballast Train - No Train Period. Min 6hrs Continuous Required | John Hilton | Adrian Unwin |  |  | 2024-03-18
IPR-2680 | 2024-04-19 | Approved | 0644-2024 | 2024-04-19 | 3 | Window Possession | Goulburn | Gunning | UP AND DOWN MAINS | 2024-05-11 07:00 | 2024-05-11 17:30 | 10:30 | Ultrasonic Testing | North - South | Goulburn to Junee | DEDICATED TESTING WINDOWS. UNHEALTHY MTP SERVICES MAY BE DELAYED. NO AD HOC SERVICES PERMITTED. | Neil Doust | David Knee
IPR-2692 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Callington | Callington | Loop | 2024-05-13 06:00 | 2024-05-13 20:00 | 14:00 | Bridge Maintenance on Crossing loop | East - West | Crystal Brook to Spencer Junction | Crossing Loop Booked Out | Bryce Gore | Bonnar Mahains |  |  | 2023-11-23
IPR-2517 | 2024-03-27 | Supported | 0539-2024 |  | 3 | Window Possession | Junee | Junee |  | 2024-05-13 10:15 | 2024-05-13 17:15 | 7:00 | Signal Gantry Ladder Replacement | North - South | Junee to Albury | No ad hoc services through window. Mandatory services to operate as planned. Late mandatories may be delayed. | Andrew Duncan | Nathaniel Gomes | JUNEE JE01 & JE02 & JE15 Signals and JUNEE JE67 & JE69 Signals. Clip and lock 125 points to exclude rail traffic from the yard |  | 2024-03-26
IPR-2693 | 2023-11-24 | Approved |  |  | 2 | Total Possession | Callington | Callington | Loop | 2024-05-14 06:00 | 2024-05-14 20:00 | 14:00 | Bridge Maintenance on Crossing loop | East - West | Crystal Brook to Spencer Junction | Crossing Loop Booked Out | Bryce Gore | Bonnar Mahains |  |  | 2023-11-23
IPR-2570 | 2024-04-05 | Supported | 0550-2024 | 2024-04-23 | 1 | Total Possession | Fisher | O'Malley | Main | 2024-05-14 07:30 | 2024-05-14 11:30 | 4:00 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | Unload of Ballast Train - No Train Period. Min 4hrs Continuous Required | John Hilton | Adrian Unwin |  |  | 2024-03-18
IPR-2542 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-14 08:00 | 2024-05-14 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2518 | 2024-03-27 | Supported | 0539-2024 |  | 3 | Window Possession | Junee | Junee |  | 2024-05-14 10:15 | 2024-05-14 17:15 | 7:00 | Signal Gantry Ladder Replacement | North - South | Junee to Albury | No ad hoc services through window. Mandatory services to operate as planned. Late mandatories may be delayed. | Andrew Duncan | Nathaniel Gomes | JUNEE JE01 & JE02 & JE15 Signals and JUNEE JE67 & JE69 Signals. Clip and lock 125 points to exclude rail traffic from the yard |  | 2024-03-26
IPR-2571 | 2024-04-05 | Supported | 0550-2024 | 2024-04-23 | 1 | Total Possession | Watson | Ooldea | Main | 2024-05-14 12:00 | 2024-05-14 15:15 | 3:15 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | Unload of Ballast Train - No Train Period. Min 3hrs Continuous Required | John Hilton | Adrian Unwin |  |  | 2024-03-18
IPR-2506 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Tailem Bend | Tailem Bend | Mainline | 2024-05-14 13:00 | 2024-05-14 22:00 | 9:00 | Magpie Drive LX Upgrade 122.335km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Bonnar Mahains |  |  | 2023-11-23
IPR-2543 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-15 08:00 | 2024-05-15 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2519 | 2024-03-27 | Supported | 0539-2024 |  | 3 | Window Possession | Junee | Junee |  | 2024-05-15 10:15 | 2024-05-15 17:15 | 7:00 | Signal Gantry Ladder Replacement | North - South | Junee to Albury | No ad hoc services through window. Mandatory services to operate as planned. Late mandatories may be delayed. | Andrew Duncan | Nathaniel Gomes | JUNEE JE01 & JE02 & JE15 Signals and JUNEE JE67 & JE69 Signals. Clip and lock 125 points to exclude rail traffic from the yard |  | 2024-03-26
IPR-2507 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Coomandook | Coomandook | Mainline | 2024-05-15 12:30 | 2024-05-15 21:45 | 9:15 | Hannah Well Rd LX Upgrade 150.209km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Bonnar Mahains |  |  | 2023-11-23
IPR-2683 | 2024-04-19 | Approved | 0656-2024 | 2024-04-19 | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-05-15 14:00 | 2024-05-15 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2553 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Cootamundra | Cootamundra | DOWN MAIN | 2024-05-16 06:30 | 2024-05-16 09:00 | 2:30 | ULTRASONIC TESTING | North - South | Goulburn to Junee | NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA01 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2544 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-16 08:00 | 2024-05-16 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2520 | 2024-03-27 | Supported | 0539-2024 |  | 3 | Window Possession | Junee | Junee |  | 2024-05-16 10:15 | 2024-05-16 17:15 | 7:00 | Signal Gantry Ladder Replacement | North - South | Junee to Albury | No ad hoc services through window. Mandatory services to operate as planned. Late mandatories may be delayed. | Andrew Duncan | Nathaniel Gomes | JUNEE JE01 & JE02 & JE15 Signals and JUNEE JE67 & JE69 Signals. Clip and lock 125 points to exclude rail traffic from the yard |  | 2024-03-26
IPR-2554 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Cootamundra | Cootamundra | UP MAIN | 2024-05-16 10:40 | 2024-05-16 12:40 | 2:00 | ULTRASONIC TESTING | North - South | Goulburn to Junee | NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2555 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Cootamundra | Harden | UP MAIN | 2024-05-16 12:35 | 2024-05-16 14:30 | 1:55 | ULTRASONIC TESTING | North - South | Goulburn to Junee | NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2572 | 2024-04-05 | Supported | 0550-2024 | 2024-04-23 | 1 | Total Possession | O'Malley | Fisher | Main | 2024-05-17 05:30 | 2024-05-17 08:20 | 2:50 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | Unload of Ballast Train - No Train Period. Min 2.5hrs Continuous Required | John Hilton | Adrian Unwin |  |  | 2024-03-18
IPR-2556 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Cootamundra | Harden | UP MAIN | 2024-05-17 06:30 | 2024-05-17 08:15 | 1:45 | ULTRASONIC TESTING | North - South | Goulburn to Junee | NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2545 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-17 08:00 | 2024-05-17 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2573 | 2024-04-05 | Supported | 0550-2024 | 2024-04-23 | 1 | Total Possession | Thomiar | Cook | Main | 2024-05-17 08:45 | 2024-05-17 12:00 | 3:15 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | Unload of Ballast Train - No Train Period. Min 3hrs Continuous Required | John Hilton | Adrian Unwin |  |  | 2024-03-18
IPR-2522 | 2024-03-27 | Supported | 0539-2024 |  | 3 | Window Possession | Harefield | Bomen | Main, Loop & Siding | 2024-05-17 10:15 | 2024-05-17 17:15 | 7:00 | Signal Gantry Ladder Replacement | North - South | Junee to Albury | No ad hoc services through window. Mandatory services to operate as planned. Late mandatories may be delayed. | Andrew Duncan | Nathaniel Gomes | HAREFIELD 01-5 Signal and BOMEN BN26 & BN28 Signals |  | 2024-03-26
IPR-2557 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Cootamundra | Harden | UP MAIN | 2024-05-17 11:10 | 2024-05-17 14:40 | 3:30 | ULTRASONIC TESTING | North - South | Goulburn to Junee | WINDOW IS DEDICATED FOR ULTRASONIC TESTING ONLY NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2558 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Harden | Cootamundra | DOWN MAIN | 2024-05-18 06:30 | 2024-05-18 08:40 | 2:10 | ULTRASONIC TESTING | North - South | Goulburn to Junee | WINDOW IS DEDICATED FOR ULTRASONIC TESTING ONLY NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2546 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-18 08:00 | 2024-05-18 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2684 | 2024-04-19 | Approved | 0656-2024 | 2024-04-19 | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-05-18 08:00 | 2024-05-18 16:30 | 8:30 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2559 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Harden | Cootamundra | DOWN MAIN | 2024-05-18 09:30 | 2024-05-18 11:40 | 2:10 | ULTRASONIC TESTING | North - South | Goulburn to Junee | WINDOW IS DEDICATED FOR ULTRASONIC TESTING ONLY NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2560 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Harden | Cootamundra | DOWN MAIN | 2024-05-18 12:40 | 2024-05-18 16:30 | 3:50 | ULTRASONIC TESTING | North - South | Goulburn to Junee | WINDOW IS DEDICATED FOR ULTRASONIC TESTING ONLY NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2547 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-19 08:00 | 2024-05-19 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2685 | 2024-04-19 | Approved | 0656-2024 | 2024-04-19 | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-05-19 09:00 | 2024-05-19 13:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2561 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Harden | Yass Jct | UP MAIN | 2024-05-19 11:30 | 2024-05-19 15:00 | 3:30 | ULTRASONIC TESTING | North - South | Goulburn to Junee | WINDOW IS DEDICATED FOR ULTRASONIC TESTING ONLY NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2602 | 2024-04-23 | Pending |  |  | 2 | Total Possession | Yarrawonga | Oaklands | Branch Line | 2024-05-20 06:00 | 2024-05-22 18:00 | 60:00 | Sleeper Train Unloading | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2024-04-08
IPR-2562 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Harden | Yass Jct | UP MAIN | 2024-05-20 06:40 | 2024-05-20 09:10 | 2:30 | ULTRASONIC TESTING | North - South | Goulburn to Junee | WINDOW IS DEDICATED FOR ULTRASONIC TESTING ONLY NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2523 | 2024-03-27 | Supported | 0539-2024 |  | 3 | Window Possession | Wagga Wagga | Wagga Wagga | Main & Loop | 2024-05-20 07:30 | 2024-05-20 15:30 | 8:00 | Signal Gantry Ladder Replacement | North - South | Junee to Albury | No ad hoc services through window. Mandatory services to operate as planned. Late mandatories may be delayed. | Andrew Duncan | Nathaniel Gomes | WAGGA WAGGA 04-3 Signal and WAGGA WAGGA 04-4 Signal |  | 2024-03-26
IPR-2548 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-20 08:00 | 2024-05-20 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2521 | 2024-03-27 | Supported | 0539-2024 |  | 3 | Window Possession | Harefield | Bomen | Main, Loop & Siding | 2024-05-20 10:30 | 2024-05-20 18:30 | 8:00 | Signal Gantry Ladder Replacement | North - South | Junee to Albury | No ad hoc services through window. Mandatory services to operate as planned. Late mandatories may be delayed. | Andrew Duncan | Nathaniel Gomes | HAREFIELD 01-5 Signal and BOMEN BN26 & BN28 Signals |  | 2024-03-26
IPR-2563 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Harden | Yass Jct | UP MAIN | 2024-05-20 11:00 | 2024-05-20 15:00 | 4:00 | ULTRASONIC TESTING | North - South | Goulburn to Junee | WINDOW IS DEDICATED FOR ULTRASONIC TESTING ONLY NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2686 | 2024-04-19 | Approved | 0656-2024 | 2024-04-19 | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-05-20 14:00 | 2024-05-20 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2564 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Yass Jct | Harden | DOWN MAIN | 2024-05-21 07:15 | 2024-05-21 11:10 | 3:55 | ULTRASONIC TESTING | North - South | Goulburn to Junee | WINDOW IS DEDICATED FOR ULTRASONIC TESTING ONLY NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2524 | 2024-03-27 | Supported | 0539-2024 |  | 3 | Window Possession | Wagga Wagga | Wagga Wagga | Main & Loop | 2024-05-21 07:30 | 2024-05-21 15:30 | 8:00 | Signal Gantry Ladder Replacement | North - South | Junee to Albury | No ad hoc services through window. Mandatory services to operate as planned. Late mandatories may be delayed. | Andrew Duncan | Nathaniel Gomes | WAGGA WAGGA 04-3 Signal and WAGGA WAGGA 04-4 Signal |  | 2024-03-26
IPR-2549 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-21 08:00 | 2024-05-21 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2565 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Harden | Yass Jct | UP MAIN | 2024-05-21 10:40 | 2024-05-21 12:40 | 2:00 | ULTRASONIC TESTING | North - South | Goulburn to Junee | WINDOW IS DEDICATED FOR ULTRASONIC TESTING ONLY NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2701 | 2024-04-23 | Supported | 0653-2024 |  | 1 | Total Possession | Pimba | Burando | Main | 2024-05-21 13:30 | 2024-05-21 19:00 | 5:30 | Unload Ballast Train | East - West | Spencer Junction to Tarcoola | No Train Period - Unload Ballast Train | John Hilton | Kristen Xiao |  | LP | 2024-04-17
IPR-2687 | 2024-04-19 | Approved | 0656-2024 | 2024-04-19 | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-05-21 14:00 | 2024-05-21 19:00 | 5:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2525 | 2024-03-27 | Supported | 0539-2024 |  | 3 | Window Possession | Wagga Wagga | Wagga Wagga | Main & Loop | 2024-05-22 07:30 | 2024-05-22 15:30 | 8:00 | Signal Gantry Ladder Replacement | North - South | Junee to Albury | No ad hoc services through window. Mandatory services to operate as planned. Late mandatories may be delayed. | Andrew Duncan | Nathaniel Gomes | WAGGA WAGGA 04-3 Signal and WAGGA WAGGA 04-4 Signal |  | 2024-03-26
IPR-2550 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-22 08:00 | 2024-05-22 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2566 | 2024-04-19 | Approved | 0572-2024 | 2024-04-19 | 3 | Window Possession | Harden | Yass Jct | UP MAIN | 2024-05-22 11:25 | 2024-05-22 15:00 | 3:35 | ULTRASONIC TESTING | North - South | Goulburn to Junee | WINDOW IS DEDICATED FOR ULTRASONIC TESTING ONLY NO AD HOC SERVICES ARE PERMITTED MANDATORY SERVICES OPERATE AS REQUIREDLATE MANDATORY TRAINS MAY BE DELAYED | Neil Doust | David Knee | COOTAMUNDRA SIGNAL CA78 TO COOTAMUNDRA END YARD LIMIT | TOA | 2024-04-04
IPR-2688 | 2024-04-19 | Approved | 0656-2024 | 2024-04-19 | 3 | Total Possession | Dry Creek | Bolivar | Main Line | 2024-05-22 14:00 | 2024-05-22 18:00 | 4:00 | VIR Project | East - West | Dry Creek to Crystal Brook | ​Adhocs with Three Days Notice and Project Approval | Bryce Gore | Michael Iannella | Signals 16 & 16E Dry Creek to Bolivar 3 |  | 2023-11-17
IPR-2526 | 2024-03-27 | Supported | 0539-2024 |  | 3 | Window Possession | Wagga Wagga | Wagga Wagga | Main & Loop | 2024-05-23 07:30 | 2024-05-23 15:30 | 8:00 | Signal Gantry Ladder Replacement | North - South | Junee to Albury | No ad hoc services through window. Mandatory services to operate as planned. Late mandatories may be delayed. | Andrew Duncan | Nathaniel Gomes | WAGGA WAGGA 04-3 Signal and WAGGA WAGGA 04-4 Signal |  | 2024-03-26
IPR-2551 | 2024-03-13 | Approved | 0549-2024 | 2024-04-05 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-23 08:00 | 2024-05-23 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2702 | 2024-04-23 | Supported | 0653-2024 |  | 1 | Total Possession | Hughes | Deakin | Main | 2024-05-24 07:00 | 2024-05-24 09:30 | 2:30 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | No Train Period - Unload Ballast Train | John Hilton | Kristen Xiao |  | LP | 2024-04-17
IPR-2527 | 2024-03-27 | Supported | 0539-2024 |  | 3 | Window Possession | Wagga Wagga | Wagga Wagga | Main & Loop | 2024-05-24 07:30 | 2024-05-24 15:30 | 8:00 | Signal Gantry Ladder Replacement | North - South | Junee to Albury | No ad hoc services through window. Mandatory services to operate as planned. Late mandatories may be delayed. | Andrew Duncan | Nathaniel Gomes | WAGGA WAGGA 04-3 Signal and WAGGA WAGGA 04-4 Signal |  | 2024-03-26
IPR-2703 | 2024-04-23 | Supported | 0653-2024 |  | 1 | Total Possession | Mundrabilla | Loongana | Main | 2024-05-24 11:00 | 2024-05-24 12:45 | 1:45 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | No Train Period - Unload Ballast Train | John Hilton | Kristen Xiao |  | LP | 2024-04-17
IPR-2704 | 2024-04-23 | Supported | 0653-2024 |  | 1 | Total Possession | Nurina | Haig | Main | 2024-05-24 13:45 | 2024-05-24 15:45 | 2:00 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | No Train Period - Unload Ballast Train | John Hilton | Kristen Xiao |  | LP | 2024-04-17
IPR-2631 | 2024-03-25 | Pending | 0601-2024 |  | 3 | Window Possession | Gunning | Yass Jct | DOWN MAIN | 2024-05-26 14:10 | 2024-05-26 17:30 | 3:20 | Ultrasonic Testing | North - South | Goulburn to Junee | DEDICATED TESTING WINDOWS. UNHEALTHY MTP SERVICES MAY BE DELAYED. NO AD HOC SERVICES PERMITTED. | Neil Doust | David Knee
IPR-2632 | 2024-03-25 | Pending | 0601-2024 |  | 3 | Window Possession | Gunning | Yass Jct | DOWN MAIN | 2024-05-27 06:50 | 2024-05-27 09:00 | 2:10 | Ultrasonic Testing | North - South | Goulburn to Junee | DEDICATED TESTING WINDOWS. UNHEALTHY MTP SERVICES MAY BE DELAYED. NO AD HOC SERVICES PERMITTED. | Neil Doust | David Knee
IPR-2633 | 2024-03-25 | Pending | 0601-2024 |  | 3 | Window Possession | Gunning | Joppa Jct | UP MAIN | 2024-05-27 13:10 | 2024-05-27 16:00 | 2:50 | Ultrasonic Testing | North - South | Goulburn to Junee | DEDICATED TESTING WINDOWS. UNHEALTHY MTP SERVICES MAY BE DELAYED. NO AD HOC SERVICES PERMITTED. | Neil Doust | David Knee
IPR-2705 | 2024-04-23 | Supported | 0654-2024 |  | 1 | Total Possession | Rawlinna | Wilban | Main | 2024-05-27 22:00 | 2024-05-28 05:00 | 7:00 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | No Train Period - Unload Ballast Train | John Hilton | Kristen Xiao |  | LP | 2024-04-17
IPR-2579 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-28 08:00 | 2024-05-28 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2634 | 2024-03-25 | Pending | 0601-2024 |  | 3 | Window Possession | Gunning | Joppa Jct | UP MAIN | 2024-05-28 09:00 | 2024-05-28 10:50 | 1:50 | Ultrasonic Testing | North - South | Goulburn to Junee | DEDICATED TESTING WINDOWS. UNHEALTHY MTP SERVICES MAY BE DELAYED. NO AD HOC SERVICES PERMITTED. | Neil Doust | David Knee
IPR-2635 | 2024-03-25 | Pending | 0601-2024 |  | 3 | Window Possession | Gunning | Joppa Jct | UP MAIN | 2024-05-28 13:10 | 2024-05-28 16:30 | 3:20 | Ultrasonic Testing | North - South | Goulburn to Junee | DEDICATED TESTING WINDOWS. UNHEALTHY MTP SERVICES MAY BE DELAYED. NO AD HOC SERVICES PERMITTED. | Neil Doust | David Knee
IPR-2636 | 2024-03-25 | Pending | 0601-2024 |  | 3 | Window Possession | Joppa Jct | Gunning | DOWN MAIN | 2024-05-29 06:10 | 2024-05-29 07:50 | 1:40 | Ultrasonic Testing | North - South | Goulburn to Junee | DEDICATED TESTING WINDOWS. UNHEALTHY MTP SERVICES MAY BE DELAYED. NO AD HOC SERVICES PERMITTED. | Neil Doust | David Knee
IPR-2580 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-29 08:00 | 2024-05-29 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2637 | 2024-03-25 | Pending | 0601-2024 |  | 3 | Window Possession | Joppa Jct | Gunning | DOWN MAIN | 2024-05-29 10:30 | 2024-05-29 12:10 | 1:40 | Ultrasonic Testing | North - South | Goulburn to Junee | DEDICATED TESTING WINDOWS. UNHEALTHY MTP SERVICES MAY BE DELAYED. NO AD HOC SERVICES PERMITTED. | Neil Doust | David Knee
IPR-2706 | 2024-04-23 | Supported | 0654-2024 |  | 1 | Total Possession | Zanthus | Goddards | Main | 2024-05-29 20:50 | 2024-05-30 00:30 | 3:40 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | No Train Period - Unload Ballast Train | John Hilton | Kristen Xiao |  | LP | 2024-04-17
IPR-2707 | 2024-04-23 | Supported | 0654-2024 |  | 1 | Total Possession | Goddards | Kitchener | Main | 2024-05-30 00:30 | 2024-05-30 02:00 | 1:30 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | No Train Period - Unload Ballast Train | John Hilton | Kristen Xiao |  | LP | 2024-04-17
IPR-2708 | 2024-04-23 | Supported | 0654-2024 |  | 1 | Total Possession | Kitchener | Boonderoo | Main | 2024-05-30 02:00 | 2024-05-30 04:30 | 2:30 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | No Train Period - Unload Ballast Train | John Hilton | Kristen Xiao |  | LP | 2024-04-17
IPR-2638 | 2024-03-25 | Pending | 0601-2024 |  | 3 | Window Possession | Joppa Jct | Gunning | DOWN MAIN | 2024-05-30 06:30 | 2024-05-30 10:00 | 3:30 | Ultrasonic Testing | North - South | Goulburn to Junee | DEDICATED TESTING WINDOWS. UNHEALTHY MTP SERVICES MAY BE DELAYED. NO AD HOC SERVICES PERMITTED. | Neil Doust | David Knee
IPR-2581 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-30 08:00 | 2024-05-30 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2582 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-05-31 08:00 | 2024-05-31 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2709 | 2024-04-23 | Supported | 0654-2024 |  | 1 | Total Possession | Karonie | Chifley | Main | 2024-05-31 18:15 | 2024-05-31 22:00 | 3:45 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | No Train Period - Unload Ballast Train | John Hilton | Kristen Xiao |  | LP | 2024-04-17
IPR-2710 | 2024-04-23 | Supported | 0654-2024 |  | 1 | Total Possession | Zanthus | Goddards | Main | 2024-05-31 23:30 | 2024-06-01 03:00 | 3:30 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | No Train Period - Unload Ballast Train | John Hilton | Kristen Xiao |  | LP | 2024-04-17
IPR-2642 | 2024-04-15 | Approved |  |  | 2 | Total Possession | Tottenham | Tottenham | Kilmore East Quarry Siding | 2024-06-01 07:00 | 2024-06-01 19:00 | 12:00 | VLine Data Changes | North - South | Albury to Somerton | No Train Period | Bryce Gore | Thiago Cavalcanti |  |  | 2024-04-03
IPR-2694 | 2024-04-23 | Pending |  |  | 3 | Window Possession | Mile End | Islington | Mainline | 2024-06-01 07:00 | 2024-06-01 19:00 | 12:00 | Mudhole Removal | East - West | Serviceton to Islington (SA) | Adhocs with 3 Days Notice and Project Approval | Bryce Gore | Kristen Xiao |  |  | 2024-04-22
IPR-2583 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-01 08:00 | 2024-06-01 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2643 | 2024-04-15 | Approved |  |  | 2 | Total Possession | Tottenham | Tottenham | Kilmore East Quarry Siding | 2024-06-02 07:00 | 2024-06-02 19:00 | 12:00 | VLine Data Changes | North - South | Albury to Somerton | No Train Period | Bryce Gore | Thiago Cavalcanti |  |  | 2024-04-03
IPR-2695 | 2024-04-23 | Pending |  |  | 3 | Window Possession | Mile End | Islington | Mainline | 2024-06-02 07:00 | 2024-06-02 19:00 | 12:00 | Mudhole Removal | East - West | Serviceton to Islington (SA) | Adhocs with 3 Days Notice and Project Approval | Bryce Gore | Kristen Xiao |  |  | 2024-04-22
IPR-2584 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-02 08:00 | 2024-06-02 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2696 | 2024-04-23 | Pending |  |  | 3 | Window Possession | Mile End | Islington | Mainline | 2024-06-03 07:00 | 2024-06-03 19:00 | 12:00 | Mudhole Removal | East - West | Serviceton to Islington (SA) | Adhocs with 3 Days Notice and Project Approval | Bryce Gore | Kristen Xiao |  |  | 2024-04-22
IPR-2585 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-03 08:00 | 2024-06-03 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2711 | 2024-04-23 | Supported | 0654-2024 |  | 1 | Total Possession | Karonie | Chifley | Main | 2024-06-03 23:30 | 2024-06-04 06:00 | 6:30 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | No Train Period - Unload Ballast Train | John Hilton | Kristen Xiao |  | LP | 2024-04-17
IPR-2714 | 2024-02-26 | Pending |  |  | 2 | Total Possession | Pimpinio Loop | Salisbury Loop | Main Line | 2024-06-04 06:00 | 2024-06-04 18:00 | 12:00 | Dimboola 7pts VX Upgrade 364.545km | East - West | Tottenham to Serviceton | ​​No Train Period | Bryce Gore | Omid Hosseini |  |  | 2024-02-20
IPR-2586 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-04 08:00 | 2024-06-04 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2587 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-05 08:00 | 2024-06-05 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2712 | 2024-04-23 | Supported | 0654-2024 |  | 1 | Total Possession | Karonie | Blamey | Main | 2024-06-05 20:20 | 2024-06-06 03:00 | 6:40 | Unload Ballast Train | East - West | Tarcoola to Kalgoorlie | No Train Period - Unload Ballast Train | John Hilton | Kristen Xiao |  | LP | 2024-04-17
IPR-2588 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-06 08:00 | 2024-06-06 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2657 | 2024-01-24 | Pending | 0634-2024 |  | 2 | Total Possession | Kiacatoo | Kiacatoo | Mainline | 2024-06-07 15:30 | 2024-06-08 01:30 | 10:00 | LX Renewal 575.824km | East - West | Goobang Junction to Broken Hill | No Train Period | Neil Doust | Angus Kirkman | Condobolin UYL to Kiacatoo UYL |  | 2024-01-21
IPR-2529 | 2022-07-26 | Supported | 0390-2024 |  | 1 | Config 9 | Taree | Grafton City | Main Line & Crossing Loops | 2024-06-08 05:30 | 2024-06-10 19:00 | 61:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | WE50 ​Closedown LPA | Neil Doust | Warren Williams | Taree 21-01 Signal to Grafton City 44-14 Signal | LPA | 2022-06-23
IPR-2530 | 2022-07-26 | Supported | 0390-2024 |  | 1 | Config 9 | Grafton City | Casino | Main Line & Crossing Loops | 2024-06-08 05:30 | 2024-06-10 17:00 | 59:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | WE50 ​Closedown LPA | Neil Doust | Warren Williams | Grafton City 44-14 Signal to Casino 52-2 Signal | LPA | 2022-06-23
IPR-2531 | 2022-07-26 | Supported | 0390-2024 |  | 1 | Config 9 | Casino | Acacia Ridge | Main Line & Crossing Loops | 2024-06-08 07:00 | 2024-06-10 19:00 | 60:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | WE50 ​Closedown LPA | Neil Doust | Warren Williams | Casino 52-2 Signal to Acacia Ridge AR1 Signal | LPA | 2022-06-23
IPR-2697 | 2024-04-23 | Pending |  |  | 3 | Window Possession | Mile End | Islington | Mainline | 2024-06-08 07:00 | 2024-06-08 19:00 | 12:00 | Mudhole Removal | East - West | Serviceton to Islington (SA) | Adhocs with 3 Days Notice and Project Approval | Bryce Gore | Kristen Xiao |  |  | 2024-04-22
IPR-2658 | 2024-01-24 | Pending | 0634-2024 |  | 2 | Total Possession | Euabalong West | Euabalong West | Mainline | 2024-06-08 16:00 | 2024-06-09 04:00 | 12:00 | LX Renewal 619.439km | East - West | Goobang Junction to Broken Hill | No Train Period | Neil Doust | Angus Kirkman | Condobolin UYL to Kiacatoo UYL |  | 2024-01-21
IPR-2691 | 2024-04-23 | Pending |  |  | 2 | Total Possession | Laverton Loop | Elders Loop | Main Line | 2024-06-08 20:00 | 2024-06-09 08:00 | 12:00 | Re-timber Manor 27W Points at 38.440km | East - West | Tottenham to Serviceton | ​​No Train Period | Bryce Gore | Omid Hosseini |  |  | 2024-04-21
IPR-2698 | 2024-04-23 | Pending |  |  | 3 | Window Possession | Mile End | Islington | Mainline | 2024-06-09 07:00 | 2024-06-09 19:00 | 12:00 | Mudhole Removal | East - West | Serviceton to Islington (SA) | Adhocs with 3 Days Notice and Project Approval | Bryce Gore | Kristen Xiao |  |  | 2024-04-22
IPR-2659 | 2024-01-24 | Pending | 0634-2024 |  | 2 | Total Possession | Euabalong West | Euabalong West | Mainline | 2024-06-09 21:30 | 2024-06-10 06:30 | 9:00 | LX Renewal 619.439km | East - West | Goobang Junction to Broken Hill | No Train Period | Neil Doust | Angus Kirkman | Condobolin UYL to Kiacatoo UYL |  | 2024-01-21
IPR-2508 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Mount Barker | Petwood | Mainline | 2024-06-10 06:00 | 2024-06-10 20:00 | 14:00 | Nairne Rd LX Upgrade 55.911km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Bonnar Mahains |  |  | 2023-11-23
IPR-2699 | 2024-04-23 | Pending |  |  | 3 | Window Possession | Mile End | Islington | Mainline | 2024-06-10 07:00 | 2024-06-10 19:00 | 12:00 | Mudhole Removal | East - West | Serviceton to Islington (SA) | Adhocs with 3 Days Notice and Project Approval | Bryce Gore | Kristen Xiao |  |  | 2024-04-22
IPR-2660 | 2024-01-24 | Pending | 0634-2024 |  | 2 | Total Possession | Euabalong West | Euabalong West | Mainline | 2024-06-10 15:00 | 2024-06-11 02:00 | 11:00 | LX Renewal 618.229km | East - West | Goobang Junction to Broken Hill | No Train Period | Neil Doust | Angus Kirkman | Condobolin UYL to Kiacatoo UYL |  | 2024-01-21
IPR-2715 | 2024-02-26 | Pending |  |  | 2 | Total Possession | Gheringhap Loop | Barwon Park Loop | Main Line | 2024-06-11 06:00 | 2024-06-11 18:00 | 12:00 | Inverleigh Siding Upgrade LH/RH Sets at down end 101.400km | East - West | Tottenham to Serviceton | ​​No Train Period | Bryce Gore | Omid Hosseini |  |  | 2024-02-20
IPR-2589 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-11 08:00 | 2024-06-11 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2509 | 2023-11-24 | Pending |  |  | 2 | Total Possession | Monarto South | Murray Bridge | Mainline | 2024-06-11 11:30 | 2024-06-11 20:30 | 9:00 | Netley Rd LX Upgrade 93.019km | East - West | Crystal Brook to Spencer Junction | No Train Period | Bryce Gore | Bonnar Mahains |  |  | 2023-11-23
IPR-2590 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-12 08:00 | 2024-06-12 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2661 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-12 09:00 | 2024-06-12 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2591 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-13 08:00 | 2024-06-13 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2662 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-13 09:00 | 2024-06-13 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2592 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-14 08:00 | 2024-06-14 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2663 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-14 09:00 | 2024-06-14 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2593 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-15 08:00 | 2024-06-15 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2716 | 2024-02-26 | Pending |  |  | 2 | Total Possession | Manor Loop | North Geelong | Main Line | 2024-06-15 20:00 | 2024-06-16 08:00 | 12:00 | Elders 27pts VX at 61.550km | East - West | Tottenham to Serviceton | ​​No Train Period | Bryce Gore | Omid Hosseini |  |  | 2024-02-20
IPR-2594 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-16 08:00 | 2024-06-16 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2599 | 2023-11-24 | Approved |  |  | 1 | Total Possession | Benalla | Somerton | All Standard Gauge Tracks | 2024-06-17 05:00 | 2024-06-17 19:00 | 14:00 | Inland Rail & Other Major Works | North - South | Albury to Somerton | ​14 hour Occupation | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-2595 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-17 08:00 | 2024-06-17 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2664 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-17 09:00 | 2024-06-17 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2596 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-18 08:00 | 2024-06-18 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2665 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-18 09:00 | 2024-06-18 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2597 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-19 08:00 | 2024-06-19 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2666 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-19 09:00 | 2024-06-19 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2598 | 2024-03-13 | Approved | 0580-2024 | 2024-04-08 | 3 | Window Possession | Bomen | Wagga Wagga | Single Main | 2024-06-20 08:00 | 2024-06-20 18:00 | 10:00 | Wagga Wagga Viaducts Retransoming Work | North - South | Junee to Albury | No Adhocs | Shannon James | Tofiq Ahmed | Signal BN 06 at 515.028km Bomen to Signal 04-6 at 522.412 km Wagga Wagga |  | 2024-03-13
IPR-2667 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-20 09:00 | 2024-06-20 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2668 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-21 09:00 | 2024-06-21 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2603 | 2024-04-23 | Pending |  |  | 2 | Total Possession | Benalla | Oaklands | Branch Line | 2024-06-24 06:00 | 2024-06-26 18:00 | 60:00 | Sleeper Train Unloading | North - South | Benalla to Oakland Line | No Train Period | Bryce Gore | Ryan Sliwinski |  |  | 2024-04-08
IPR-2669 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-24 09:00 | 2024-06-24 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2670 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-25 09:00 | 2024-06-25 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2671 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-26 09:00 | 2024-06-26 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2672 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-27 09:00 | 2024-06-27 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2673 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-06-28 09:00 | 2024-06-28 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2674 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-07-01 09:00 | 2024-07-01 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2675 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-07-02 09:00 | 2024-07-02 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2676 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-07-03 09:00 | 2024-07-03 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2677 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-07-04 09:00 | 2024-07-04 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2678 | 2022-12-21 | Pending |  |  | 2 | Total Possession | Longwood | Seymour | East Track | 2024-07-05 09:00 | 2024-07-05 17:00 | 8:00 | Inland Rail - Seymour Avenal Rd Eastern Abutment Works | North - South | Albury to Somerton | ​​SLR on West Track between 0700 - 1700 Monday - Friday | Bryce Gore | Tanishq Sarkar |  |  | 2022-10-12
IPR-2574 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Wangaratta | Wangaratta | All Tracks | 2024-07-15 03:00 | 2024-07-15 21:00 | 18:00 | Inland Rail - Wangaratta Station - Major Works | North - South | Albury to Somerton | ​18 hour Absolute Occupation - No Train Period of both East & West Track | Bryce Gore | Tanishq Sarkar |  |  | 2024-03-21
IPR-2713 | 2023-11-24 | Pending |  |  | 1 | Total Possession | Benalla | Somerton | All Standard Gauge Tracks | 2024-07-15 05:00 | 2024-07-15 19:00 | 14:00 | Inland Rail & Other Major Works | North - South | Albury to Somerton | ​14 hour Occupation | Bryce Gore | Tanishq Sarkar |  |  | 2023-11-21
IPR-2492 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Taree | Grafton City | All Lines | 2024-08-03 04:30 | 2024-08-05 19:30 | 63:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Stage 2 - Taree (Inclusive) to Grafton City (Exclusive) | Neil Doust | Warren Williams |  | LPA | 2023-11-11
IPR-2493 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Grafton City | Casino | All Lines | 2024-08-03 05:30 | 2024-08-05 17:00 | 59:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Stage 3 - Grafton City (Inclusive) to Casino (Inclusive) | Neil Doust | Warren Williams |  | LPA | 2023-11-11
IPR-2494 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Casino | Acacia Ridge | All Lines | 2024-08-03 07:00 | 2024-08-05 19:00 | 60:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Stage 4 - Casino (Exclusive) to Acacia Ridge (Exclusive) | Neil Doust | Warren Williams |  | LPA | 2023-11-11
IPR-2689 | 2024-04-23 | Pending |  |  | 2 | Total Possession | Berrybank Loop | Tooli Loop | Mainline | 2024-08-14 06:00 | 2024-08-14 18:00 | 12:00 | Re-Railing | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Derek Rowan |  |  | 2024-04-15
IPR-2690 | 2024-04-23 | Pending |  |  | 2 | Total Possession | Berrybank Loop | Tooli Loop | Mainline | 2024-08-15 06:00 | 2024-08-15 18:00 | 12:00 | Re-Railing | East - West | Tottenham to Serviceton | No Train Period | Bryce Gore | Derek Rowan |  |  | 2024-04-15
IPR-2700 | 2024-04-23 | Pending |  |  | 1 | Total Possession | Birkenhead | Outer Harbor | All Lines | 2024-08-31 06:00 | 2024-09-01 18:00 | 36:00 | SAPN Power Supply | East - West | Outer Harbour Line | No Train Period | Bryce Gore | Darren Schulz |  |  | 2024-04-22
IPR-2644 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Cooks River | Enfield | Down Goods | 2024-08-31 08:00 | 2024-08-31 18:00 | 10:00 | Sydney Metro Construction Activities | North - South | Sydney MFN | Possession of the Down Goods between Cooks River & Enfield. Clear of Cooks River & Enfield Yards. NO Access from the Illawarra Lines Botany to Cooks River Remains OPEN. Impacts to: 1155 (PN), 1297 (PN), 1902 (RC), 9138 (PN), 1157 (PN), 1293 (PN). | Shannon James | Steven Payne |  | LPA | 2024-04-10
IPR-2648 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-08-31 08:00 | 2024-08-31 11:30 | 3:30 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open.Impacted Services: 1152 (PN), 2192 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2652 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-08-31 15:00 | 2024-08-31 18:00 | 3:00 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 2196 (PN), 1156 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2645 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Cooks River | Enfield | Down Goods | 2024-09-01 08:00 | 2024-09-01 18:00 | 10:00 | Sydney Metro Construction Activities | North - South | Sydney MFN | Possession of the Down Goods between Cooks River & Enfield. Clear of Cooks River & Enfield Yards. NO Access from the Illawarra Lines Botany to Cooks River Remains OPEN. Impacts to: 1297 (PN), 1155 (PN), 9102 (RC), 9138 (PN), 1157 (PN), 1293 (PN) | Shannon James | Steven Payne |  | LPA | 2024-04-10
IPR-2649 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-09-01 08:00 | 2024-09-01 11:30 | 3:30 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 1152 (PN), 2192 (PN), 1907 (RC), 2196 (PN) In conjunction with Down Goods LPA Handback window from 1130 to 1500 | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2653 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-09-01 15:00 | 2024-09-01 18:00 | 3:00 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 1156 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2646 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Cooks River | Enfield | Down Goods | 2024-09-14 08:00 | 2024-09-14 18:00 | 10:00 | Sydney Metro Construction Activities | North - South | Sydney MFN | Possession of the Down Goods between Cooks River & Enfield. Clear of Cooks River & Enfield Yards. NO Access from the Illawarra Lines Botany to Cooks River Remains OPEN. Impacts to: 1155 (PN), 1297 (PN), 1902 (RC), 9138 (PN), 1157 (PN), 1293 (PN). | Shannon James | Steven Payne |  | LPA | 2024-04-10
IPR-2650 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-09-14 08:00 | 2024-09-14 11:30 | 3:30 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open.Impacted Services: 1152 (PN), 2192 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2654 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-09-14 15:00 | 2024-09-14 18:00 | 3:00 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 2196 (PN), 1156 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2647 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Cooks River | Enfield | Down Goods | 2024-09-15 08:00 | 2024-09-15 18:00 | 10:00 | Sydney Metro Construction Activities | North - South | Sydney MFN | Possession of the Down Goods between Cooks River & Enfield. Clear of Cooks River & Enfield Yards. NO Access from the Illawarra Lines Botany to Cooks River Remains OPEN. Impacts to: 1297 (PN), 1155 (PN), 9102 (RC), 9138 (PN), 1157 (PN), 1293 (PN) | Shannon James | Steven Payne |  | LPA | 2024-04-10
IPR-2651 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-09-15 08:00 | 2024-09-15 11:30 | 3:30 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 1152 (PN), 2192 (PN), 1907 (RC), 2196 (PN) In conjunction with Down Goods LPA Handback window from 1130 to 1500 | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2655 | 2024-04-23 | Supported |  |  | 1 | Total Possession | Enfield | Cooks River | Up Goods | 2024-09-15 15:00 | 2024-09-15 18:00 | 3:00 | Sydney Metro Construction | North - South | Sydney MFN | Possession Clear of Cooks River & Enfield Yards. Access to Marrickville Junction Closed. Cooks River to Botany is Open. Impacted Services: 1156 (PN) In conjunction with Down Goods LPA | Shannon James | Steven Payne |  | TOA | 2024-04-10
IPR-2495 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Taree | Grafton City | All Lines | 2024-11-02 05:00 | 2024-11-03 19:30 | 38:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Taree (Inclusive) to Grafton City (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2496 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Grafton City | Casino | All Lines | 2024-11-02 05:30 | 2024-11-03 17:00 | 35:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Grafton City (Inclusive) to Casino (Inclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2497 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Casino | Acacia Ridge | All Lines | 2024-11-02 07:00 | 2024-11-03 18:00 | 35:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Casino (Exclusive) to Acacia Ridge (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2503 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Taree | Grafton City | All Lines | 2025-02-08 05:00 | 2025-02-09 19:30 | 38:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Taree (Inclusive) to Grafton City (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2500 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Grafton City | Casino | All Lines | 2025-02-08 05:30 | 2025-02-09 17:00 | 35:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Grafton City (Inclusive) to Casino (Inclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2499 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Casino | Acacia Ridge | All Lines | 2025-02-08 07:00 | 2025-02-09 18:00 | 35:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Casino (Exclusive) to Acacia Ridge (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2502 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Taree | Grafton City | All Lines | 2025-05-17 05:00 | 2025-05-18 19:30 | 38:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Taree (Inclusive) to Grafton City (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2501 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Grafton City | Casino | All Lines | 2025-05-17 05:30 | 2025-05-18 17:00 | 35:30 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Grafton City (Inclusive) to Casino (Inclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11
IPR-2498 | 2023-11-24 | Supported |  |  | 1 | Config 9 | Casino | Acacia Ridge | All Lines | 2025-05-17 07:00 | 2025-05-18 18:00 | 35:00 | Major Maintenance | North - South | Telarah to Acacia Ridge | Aligned Config 9 with Hunter Valley Mains & Sydney Trains. Casino (Exclusive) to Acacia Ridge (Exclusive) | Shannon James | Warren Williams |  | LPA | 2023-11-11